## Phase 1 - Business Setup
ROTISSERIE CHICKEN RESTAURANT STARTUP CHECKLIST
PHASE 1: BUSINESS SETUP & TAXES (weeks 1-4)
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Zoning check before signing: restaurant use, Type I hood, gas service and seats | Owner / Code consultant | Before signing the lease | Ask the city planning (zoning) office whether the zoning allows a restaurant with rotisseries and fryers, whether the space can take a Type I hood with a duct up to the roof, and what occupancy load it allows. Then ask the fire marshal in writing what the hood and fire suppression requirements are. With no exhaust path to the roof, there are no rotisseries or fryers.
☐ | Decide gas or charcoal rotisseries BEFORE signing the lease (charcoal = solid fuel: dedicated exhaust, NFPA 96, listed appliance) | Owner | Before signing the lease | Gas rotisseries (the plan's case) work with a standard Type I hood and gas service installed by a licensed gas contractor. A charcoal rotisserie, like the oven of a Peruvian pollo a la brasa place, is a solid-fuel appliance under NFPA 96: it needs its own exhaust, a spark arrester and daily ash removal, and the fire marshal will want a listed (UL/ETL) appliance, plus NSF/ANSI 4 certification for the health department. Rotisseries imported from Peru may have no listing, and air quality rules vary: ask your air district. It is a product decision, not a decoration one: ask the fire marshal in writing whether your space can take it.
☐ | Size the rotisseries with your Sunday count (48 birds per load, loads of 75-90 minutes) | Owner | Before signing the lease | With the "Rotisserie" tab of the kit's calculator: how many chickens you sell on Sunday, how many fit per load and how many loads you can run before the Sunday lunch peak. The plan uses two 8-spit gas rotisseries (48 birds per load each); peak months and holidays run tight. The rotisseries have to fit in the space together with their Type I hood.
☐ | Choose your legal structure: LLC vs S corp | Accountant | Week 1 | The financial plan assumes an effective income tax rate of 25% (21% federal plus state), as for a C corporation. An LLC taxed as a pass-through pays through your personal return instead, and early losses carry forward as net operating losses. Compare an LLC vs S corp election with your CPA, using the plan's numbers.
☐ | Form the LLC with your state and get the EIN | Attorney / CPA | Weeks 1-2 | Filing fees, annual reports and franchise taxes vary by state. Check your Secretary of State's website before you file.
☐ | Business license + sales tax permit (state and city) | Accountant | Week 2 | Register with your state revenue department for a sales tax permit and with your city or county for a business license. Some states also ask for a separate food seller or retail license. Rules, fees and timing vary by state, so confirm them with your CPA before you open and collect sales tax from your first sale.
☐ | State payroll and unemployment registration (and workers' comp insurance) | Accountant | Week 2 | Premiums depend on your state, your payroll and your job classes. Get quotes from your insurance broker or the state fund.
☐ | Apply for the beer & wine license (state + local) | Owner | Week 1 | Start in week 1: ask your state alcohol beverage control (ABC) agency and your city what they need, and file as soon as you sign the lease: state and local approval can take months, and costs and timelines vary widely. Never open counting on it, and add liquor liability to your insurance.
☐ | Business bank account and business card | Owner | Week 2 | Keep them separate from personal accounts: card terminal settlements, delivery marketplace payouts and supplier payments all run through them.
☐ | Accountant / bookkeeper and a POS that reports sales tax | Owner | Weeks 2-4 | Payroll and onboarding for your team. Pick a POS that calculates and reports sales tax by jurisdiction before you buy it, and ask your CPA how often your state wants sales tax returns.
☐ | Take the plan to two SBA 7(a) lenders and compare loan offers | Owner | Weeks 2-4 | Bring the complete financial plan, with the month-by-month cash flow. Ask for quotes on equipment leasing for the rotisseries, the walk-in cooler and the fryers, and ask each lender about the SBA Microloan (up to $50,000) as a complement. Lenders usually expect an owner equity injection (often around 10% for SBA start-ups; many want 20-30%).
☐ | General liability, liquor liability, property and workers' comp insurance | Insurance broker | Before construction | Get quotes for general liability, liquor liability (if you will serve beer and wine), property and workers' comp. Tell the broker you cook on gas with rotisseries and fryers, and ask about equipment breakdown and spoilage coverage for the walk-in cooler.
| Tasks completed: | 0 | of | 12

## Phase 2 - Hood, Gas & Permits
ROTISSERIE CHICKEN RESTAURANT STARTUP CHECKLIST
PHASE 2: SITE, HOOD, GAS & PERMITS (weeks 3-14)
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Choose the space: second-generation restaurant space of about 1,600 sq ft (149 sq m) with a route for the Type I hood up to the roof | Owner | Weeks 3-6 | Kitchen and rotisserie area visible from the street, a counter with a heated display, a dining room with 40 seats, restrooms (one ADA-accessible) and storage. A residential neighborhood with family foot traffic on weekends and easy parking for pickup orders.
☐ | Check the electrical service and the gas capacity | Electrician / Utility | Before signing | Refrigeration, exhaust fans, HVAC and the dishwasher on electric service; rotisseries, fryers and range on gas (natural or propane). Two rotisseries of about 177,500 BTU each plus the fryers need a gas service and regulator sized for the load, with a gas permit. Ask the utility for the lead time and the cost.
☐ | Confirm the hood and duct route to the roof with your mechanical contractor | Architect / engineer | Before signing | Dedicated Type I hood and a continuous, grease-tight duct up to the roof, through a shaft or an exterior wall, with the landlord's written approval if it crosses common areas. Ask your mechanical contractor for the exhaust airflow and the makeup air.
☐ | Negotiate the lease: free-rent period during build-out and security deposit | Owner | Before signing | The plan counts two months of rent before opening and a two-month security deposit. Ask for free rent while the build-out, the hood and the gas work last.
☐ | Lease with restaurant use, hood rights and a beer & wine license contingency | Owner / Attorney | Week 6 | It should say "restaurant" or "rotisserie chicken restaurant with kitchen", authorize the build-out and the duct to the roof, and let you out of the lease if you cannot get your beer & wine license.
☐ | Commission architect and MEP drawings, including the hood and duct | Architect / Engineer | Weeks 6-8 | Kitchen and counter layout, electrical load, occupancy, ventilation, ADA accessibility, the gas installation and the hood and duct route to the roof. Ask your city (and your air district, if there is one) for its fire, mechanical and air quality requirements.
☐ | Zoning approval and certificate of occupancy | Owner / City planning office | Before construction | Zoning approval and the certificate of occupancy come from your city or county, and the rules vary. In your zoning check, ask which approvals your space needs (change of use, building permit, fire marshal sign-off) and in what order.
☐ | Building permit for the build-out and the hood | Owner / City planning office | Weeks 6-8, before construction starts | The build-out and the hood run through their own building permit and inspections: ask the building department which drawings and sign-offs they require.
☐ | Licensed gas contractor, gas permit and inspection for two rotisseries + fryers | Licensed gas contractor | During construction | Gas permit, pressure test and final inspection of the lines and appliances, and a regulator and meter sized for the rotisseries, fryers and range. Keep the paperwork: the fire marshal, the health department and your insurer may ask for it. Work by an unlicensed installer will not pass inspection.
☐ | Type I hood, UL 300 suppression and makeup air (charcoal: separate solid-fuel exhaust and spark arrester) | Installer / Engineer | Weeks 8-12 | Over the rotisseries and fryers: Type I hood with grease filters, UL 300 fire suppression system and makeup air, installed to your local fire and mechanical code. With charcoal or wood (solid fuel), NFPA 96 asks for a dedicated exhaust, a spark arrester and daily ash removal; with gas rotisseries, the standard hood is enough. Ask your air district about particulate rules.
☐ | Build-out with smooth, cleanable surfaces in the kitchen and prep areas | Contractor | Weeks 8-12 | Smooth, cleanable walls, non-slip floors (also around the rotisseries), cleanable ceilings, hands-free handwashing sinks, restrooms (one ADA-accessible) and sound insulation if you have neighbors.
☐ | Plumbing, grease interceptor and HVAC | Installer | Weeks 8-12 | Hot and cold water in the kitchen, floor drains with a grease interceptor (the rotisseries and fryers produce a lot of grease) and HVAC for the dining room.
☐ | Fire marshal sign-off of the hood and suppression system + Class K extinguisher | Installer | Weeks 10-12 | Hood with exhaust fan and grease filters covering the whole cooking line, tied to the dedicated duct, with a UL 300 suppression system and a Class K extinguisher. Ask the installer for the airflow, the makeup air and the filter cleaning plan. The fire marshal inspects it before you can cook.
☐ | Electrical final inspection and certificate of occupancy | Licensed electrician / Inspector | During and after construction | The final sign-offs (electrical, gas, mechanical, fire and building) and the certificate of occupancy. Keep them together with the gas paperwork: your health department and your insurer may ask for them.
☐ | Sign permit; rotisseries visible from the street; pre-order phone and website on the sign | Owner / Sign maker | Weeks 10-14 | Ask in your zoning check whether your city requires a separate sign permit. Put the pre-order phone number and the website where they can be read from the street.
| Tasks completed: | 0 | of | 15

## Phase 3 - Rotisserie & Health
ROTISSERIE CHICKEN RESTAURANT STARTUP CHECKLIST
PHASE 3: KITCHEN, ROTISSERIES & HEALTH PERMIT (weeks 6-14)
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Buy listed equipment (UL/ETL, NSF/ANSI 4): two gas rotisseries, heated display, fryers, range | Owner | Weeks 6-8 | Two 8-spit gas rotisseries (a Pegasus CR-8G lists at $6,011 retail and holds 48 birds per load; the plan budgets $13,000 for the pair with freight and installation), a heated display that holds 135 °F (57 °C) or above, two fryers and a range. Ask for the technical data sheet, birds per spit, gas consumption, lead time and installation.
☐ | Walk-in, prep table and reach-in freezer | Owner | Weeks 8-10 | Walk-in cooler for raw and marinated chicken at 41 °F (5 °C) or below, a reach-in freezer and a refrigerated case that keeps the sides at the counter at 41 °F (5 °C) or below.
☐ | Submit your plans for health department plan review, apply for the health permit and book the pre-opening inspection | Owner / Health department | Before construction starts | Apply to your local health department for plan review (Food Code 8-201.11) before construction, then for the health permit and the pre-opening inspection. Selling chicken or sauces to other businesses can fall under a different license: ask your health department.
☐ | Raw and marinated chicken at 41 °F (5 °C) or below, on the bottom shelf, date-marked (WOG: no giblets) | Consultant / Owner | Before opening | Buy USDA-inspected chicken from an approved source and receive it at 41 °F (5 °C) or below; the marinated raw chicken is held at 41 °F (5 °C) or below as well, below any ready-to-eat food. The plan buys birds WOG (without giblets), so there are no giblets to store. Log the temperature at every delivery.
☐ | Separate raw-chicken prep sink and table, color-coded boards, never wash raw chicken | Rotisserie lead | Before opening | Spit and marinate on a stainless-steel table SEPARATE from the one you serve from, with its own boards and utensils. Raw chicken is not washed: it splashes and contaminates the area.
☐ | Get your county's rules for cooking and hot holding chicken in writing and write your rotisserie SOP: probe the thigh at 165 °F (74 °C) and log it | Rotisserie lead | Before opening | Each state adopts its own edition of the FDA Food Code and your county may add rules. The Food Code requires poultry to reach 165 °F (74 °C) (3-401.11); the plan's SOP probes the thickest part of the thigh on every load and logs it. Browned outside does not mean done next to the bone.
☐ | Heated display at 135 °F (57 °C) or above, time marked on every load (4-hour limit; TPHC only with a written procedure) | Counter lead / cashier | Before opening | Hot holding is 135 °F (57 °C) or above (Food Code 3-501.16). The plan's SOP keeps the display hot and marks the time on every load: at 4 hours, or if a bird drops below 135 °F, cool it at once with a log for tomorrow's sandwich or bowl, or throw it out. Never put it back in the display without reheating it to 165 °F (74 °C). Under time as a public health control instead (TPHC, 3-501.19), with the time marked and a written procedure, the chicken is thrown out at 4 hours, never cooled.
☐ | Leftover chicken cooled from 135 °F (57 °C) to 70 °F (21 °C) in 2 hours and to 41 °F (5 °C) within 6 hours, logged; reheat to 165 °F | Rotisserie cook | Before opening | What is left at closing is either held at 135 °F (57 °C) or above or cooled from 135 °F to 70 °F in 2 hours and to 41 °F within 6 hours in total (3-501.14). Reuse it the next day in the sandwich or bowl, reheated to 165 °F (74 °C) for hot holding (3-403.11). Log how many birds are left every day.
☐ | Aji verde, huancaina and other sauces: TCS foods at 41 °F (5 °C) or below, date-marked | Rotisserie cook | Before opening | Sauces made with mayonnaise, fresh cheese or evaporated milk are TCS (time/temperature control for safety) foods: keep them at 41 °F (5 °C) or below, date-mark them and discard them on time. Cooked rice and beans are TCS foods too (B. cereus): keep them at 135 °F (57 °C) or above. No raw egg in any sauce unless it is pasteurized.
☐ | Label the birds and sides you pack for self-service (3-602.11) | Owner | Before opening | A whole chicken bagged in the heated display for self-service, or sides packed ahead, need a label with the name of the food, the ingredients with the major allergens, the net quantity, and your business name and address (Food Code 3-602.11; check your state's rules). Food bagged to order and handed over by staff does not need the full label, but still tell the customer about allergens.
☐ | Traceability and records: lots, temperatures and suppliers | Owner | From the first purchase | Lot and date of the chicken, receiving temperature, cooler temperatures, probe temperatures, display temperatures, cooling logs for leftovers and the supplier of every ingredient.
☐ | Recipe cards with the 9 major allergens (soy and wheat in the marinade; milk and egg in the sauces) | Rotisserie lead | Before opening | Marinade (soy and wheat from the soy sauce, wheat or barley if it has beer), aji verde (egg and milk, depending on the recipe), huancaina (milk, and wheat from the crackers), sandwich bun (wheat; sesame if it has seeds) and fries or yuca fries from a shared fryer (cross-contact). With the kit's calculator, the cost of each one.
☐ | Allergens on delivery marketplaces and on your website | Owner | Before you sign up | On delivery marketplaces and on your own website, allergens must be visible before the customer orders. Check the listing of each product on each platform.
☐ | Temperature of orders leaving the shop | Owner | Before the first order | Insulated bags and packaging that keep the food hot (135 °F (57 °C) or above) in transit, also for marketplace delivery: a whole chicken travels well, fries do not.
| Tasks completed: | 0 | of | 14

## Phase 4 - Staff & Allergens
ROTISSERIE CHICKEN RESTAURANT STARTUP CHECKLIST
PHASE 4: STAFF, TRAINING, SAFETY & ALLERGENS (weeks 10-14)
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Set pay rates against the state and local minimum wage and post the labor law posters | Accountant | Week 10 | The federal minimum wage is $7.25/h, but your state or city may be higher: use the highest. The plan assumes at least $15/h for everyone; put your actual lowest hourly rate in the "0. Assumptions" tab of the financial plan.
☐ | Offer letters for full-time and part-time staff | Accountant | Before opening | With schedule, pay rate and role. Collect a W-4 and an I-9 (with identity documents) from every hire, the I-9 within 3 business days of the start date. Classify people correctly: a 1099 contractor who works your schedule at your address is a misclassification risk.
☐ | Hire the second rotisserie cook before opening (7 days) | Owner | Weeks 10-12 | Have them learn with you to spit, load, probe and carve before opening. If only you can run the rotisseries, one sick day closes you on Sunday, your peak day.
☐ | Time clock and overtime records | Owner | From the first hire | Keep hours for every employee, part-time included (FLSA recordkeeping). A time clock in the POS makes it simple; agree with your CPA how to store the records.
☐ | Sunday and peak-day schedule (2 rotisserie cooks + 3 on the counter) | Owner | Week 12 | The shop is open 7 days and Sunday is the peak. Schedule two rotisserie cooks and three people on the counter, plus dish and prep, and treat holidays like a Sunday.
☐ | Own delivery drivers: W-2 employees only | Accountant | If you deliver yourself | Your own drivers are employees on payroll (W-2), and because they drive their own cars on your behalf you also need hired and non-owned auto insurance (check your state). Do not treat them as independent contractors. Drivers for DoorDash, Uber Eats and Grubhub work for the marketplace, not for you.
☐ | Food handler cards and a Certified Food Protection Manager (CFPM) | Owner | Before opening | Check what your state requires: a Certified Food Protection Manager on site (Food Code 2-102.12) and food handler cards for the staff. Train on handwashing, raw and cooked separation, probe temperatures, display and cooling logs, allergens and cross-contact.
☐ | Rotisserie training: spitting, loading, probing at 165 °F (74 °C), carving | Owner | Before opening | Sizing and trussing the bird, spitting with no gaps, load order, thigh probe and carving into halves and quarters. It is an investment, not an expense.
☐ | OSHA basics: safety plan and training | Insurance carrier / Consultant | Before opening | Cover the main hazards: burns from the rotisseries, hot spits and fryers, cuts when carving and spitting, gas, heat and lifting. OSHA expects a written safety plan and training.
☐ | Employee health policy and first aid | Insurance carrier / Consultant | At hire | Have every new hire sign an employee health agreement (report illness symptoms; Food Code 2-201) and stock a first aid kit.
☐ | Allergen information on the menu or by staff script, with a written record | Owner | Before opening | In writing on the menu or, if staff give it verbally, backed by a written record kept on site and a sign telling guests to ask. Keep one allergen matrix up to date for the whole menu.
☐ | Allergen notice at the counter and online | Counter lead / cashier | Before opening | Each marinade, sauce and side with its allergens in plain view of the customer: soy and wheat in the marinade, egg in the aji verde and milk in the huancaina, depending on your recipe. Review it whenever a recipe changes.
☐ | Never promise "gluten-free" with a shared fryer (21 CFR 101.91) | Owner | Before printing the menu | Under the FDA rule (21 CFR 101.91), "gluten-free" means less than 20 ppm of gluten as served. The marinade has soy sauce and beer (wheat, barley), and yuca fries or fries cooked in the same fryer as breaded items break the promise. Disclose the allergens and the cross-contact; do not promise it.
| Tasks completed: | 0 | of | 13

## Phase 5 - Menu & Pre-Orders
ROTISSERIE CHICKEN RESTAURANT STARTUP CHECKLIST
PHASE 5: MENU, BRAND, PRE-ORDERS & SUPPLIERS (weeks 8-16)
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Choose your style (Peruvian pollo a la brasa in the case) and your menu | Owner | Week 8 | A weekend take-out rotisserie, a neighborhood counter-service rotisserie chicken restaurant (this plan), peri-peri chicken or charcoal Peruvian chicken: each with a different investment, space and margin. Food trucks have their own plan: the Food Truck Business Plan Kit.
☐ | Short menu (quarter, half, whole, family meal, sandwich/bowl) costed with the calculator | Rotisserie lead | Weeks 10-14 | Cost the quarter, half and whole chicken and every combo (with yuca fries, with rice & beans, the Sunday family meal): the chicken alone leaves little, the margin is in what goes with it. Use the kit's Rotisserie Chicken Yield & Costing Calculator.
☐ | Sales tax on the menu: one rate; check your state's to-go rules | CPA / Owner | Before opening | The plan uses a single sales tax rate (8% as an example). Some states tax to-go food differently from dine-in, so check your state and city rates with your CPA and set them up in the POS and on every delivery marketplace.
☐ | Utensils and napkins on request for to-go orders | Owner | Before opening | Hand out utensils and napkins only when guests ask for them, and keep the to-go containers in stock; check your city's packaging rules.
☐ | Local packaging ordinances: fees and bans | Owner | Before opening | Some cities and states ban or charge for single-use plastic bags, foam containers and utensils. Check your city's rules before you order family-meal boxes, vented clamshells, foil bags and sauce cups.
☐ | Two USDA-inspected chicken suppliers (fixed 3.0 lb (1.4 kg) WOG birds, received at 41 °F (5 °C) or below) | Owner | Weeks 8-12 | Birds of a fixed size, 3.0 lb (1.4 kg) WOG, received at 41 °F (5 °C) or below and logged. The price of chicken moves during the year: two suppliers and the price in writing. An uneven size throws off your loads and your costing.
☐ | Frozen yuca and fries, oil, packaging, sodas and a beer & wine distributor | Owner | Weeks 10-14 | Frozen or fresh yuca and potatoes (fresh lowers the cost but needs peeling and cutting), high-oleic frying oil, family-meal boxes, vented clamshells and sauce cups. The plan estimates them with reference prices: put your own.
☐ | Used cooking oil pickup and drip-tray grease | Owner | Before opening | Contract with a licensed waste / grease hauler to pick up the oil from the fryers and the grease from the rotisserie drip trays, with a receipt for every pickup. Never down the drain.
☐ | Pre-order system: phone, online ordering, pickup slots and deposits for party trays | Owner | Before opening | Pre-orders with name, phone number and pickup time, closed on Saturday for Sunday: that tells you how many birds to load. A sign at the counter and the phone number on the bags.
☐ | Sign up with the delivery marketplaces (DoorDash, Uber Eats, Grubhub) | Owner | Before opening | Read the commission (it changes with the marketplace, the plan tier and the zone), how often they pay out, who funds the promotions and what the tablet costs. Set a ceiling for marketplace sales and track it every month. Pickup at the counter pays no commission: push it with price.
☐ | Trademark search and registration (USPTO) | Owner | Weeks 2-8 | Run a trademark search first to make sure the name is not registered in your class (restaurant services), and check your state's business name registry.
☐ | Brand, photos and website with menu, allergens and pre-orders | Designer | Weeks 8-14 | Real photos of the rotisseries and the combos; a website with the menu, allergens, hours, the pre-order phone number and a privacy policy for each channel.
☐ | Google Business Profile, Yelp, Instagram + music licensing (ASCAP/BMI/SESAC) | Owner | Before opening | Opening hours, photos of the rotisseries and a reply to every review. If you play music, you need performing-rights licenses (ASCAP, BMI, SESAC).
| Tasks completed: | 0 | of | 13

## Phase 6 - Opening & 90 Days
ROTISSERIE CHICKEN RESTAURANT STARTUP CHECKLIST
PHASE 6: OPENING & FIRST 90 DAYS
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Open in January, Month 1 of the plan | Owner | Month 1 | The plan starts in January and the ramp-up falls on the slowest months, January and February: that is why working capital matters. If you open in another month, rotate the seasonality row of the "12-Month Cash Flow" tab.
☐ | Pest control | Licensed pest control operator | Before opening | Contract with a licensed pest control operator: it is part of the prerequisites of your written food safety plan.
☐ | Cleaning plan for kitchen, rotisseries and display | Owner | Before opening | Rotisseries, spits and drip tray, fryers, hood filters, heated display, raw-chicken table and refrigeration, with a log.
☐ | Test loads with the full menu (time each load) | Rotisserie lead | Week before opening | Several test loads to tune the marinade, the cooking time, the probe and the carving, and a rehearsal Sunday with pre-orders from friends before you open.
☐ | Check temperatures and records on day one | Owner | Day 1 | Walk-in, thigh probe on every load, heated display, cooling of leftovers, sauces and the cleaning sheet; fix any deviation before you serve.
☐ | Health inspection: written food safety plan and records at hand | Owner | From day 1 | Allergen cards, labels on packaged food, traceability, temperature, cooling and cleaning logs, training records and pest control.
☐ | Hood cleaning schedule (NFPA 96) | Owner / Maintenance contractor | From month 1 | NFPA 96 sets the frequency by cooking volume and fuel: the plan budgets quarterly cleanings by a certified company because of the rotisserie grease (solid fuel such as charcoal means monthly). Keep every cleaning report, and clean the grease filters as your cleaning plan says.
☐ | Fire suppression inspection every 6 months and annual rotisserie and gas service | Licensed gas contractor | On a set calendar | The fire suppression system is inspected every 6 months, and the burners, motor and spits of the rotisseries get a service once a year, with the gas lines checked by your licensed gas contractor. Write down the dates.
☐ | Measure cooked yield and load time and recalculate (calculator) | Rotisserie lead | Weeks 1-12 | Weigh five raw and cooked chickens from the same load, time a full load and note the birds left at closing; take the averages to the calculator. The cooked yield and the load time in the plan are Kit estimates.
☐ | Holiday pre-order plan: Mother's Day, Super Bowl Sunday, Christmas Eve and New Year's Eve (pickup slots, deposits, order cap = rotisserie capacity, whole crew) | Owner | A month before each holiday | Mother's Day, Super Bowl Sunday, Christmas Eve and New Year's Eve are pre-order peaks, and May, July and December are the plan's busiest months. Prepare the schedule, the loads and the chicken order early.
☐ | Review the delivery marketplace statement each month | Owner | Monthly | Sales, commission, promotions and packaging: if marketplace sales grow, or their margin does not cover the commission, cut back or raise prices. Own delivery only with W-2 drivers and when the volume pays for it.
☐ | Compare actual sales and costs with the plan each month | Owner | Monthly | Covers per day, average check, birds sold, cost of goods and labor against the P&L in the Excel; review your costing whenever the price of chicken changes.
☐ | Track cash flow month by month and the minimum balance | Owner | Monthly | January and February are the slowest months and coincide with the launch: look at the balance of each month before a big payment.
| Tasks completed: | 0 | of | 13

## Instructions
INSTRUCTIONS FOR USE
This file is part of the Rotisserie Chicken Restaurant Business Plan Kit by AI Chef Pro.
The GREEN cells are the editable ones: change those and the rest of the workbook recalculates on its own.
OK column: choose ✓ (done), ☐ (pending) or N/A (not applicable). N/A items do not count toward the total.
Each tab's counter counts only the ✓; N/A items come out of the total.
To edit a cell that is not green: Review → Unprotect Sheet (there is no password).
More templates and kits in the catalog at aichef.pro/en/digital-products
Designed by John Guerrero — chef and restaurant consultant since 2010, in the kitchen since age 17 · johnguerrero.es
Version 2.2 · October 2026 · aichef.pro/en/digital-products/rotisserie-chicken-restaurant-business-plan · info@aichef.pro
Planning tool, not financial, tax or legal advice. Requirements vary by state, county and city — check with your accountant and local authorities. This checklist is a starting point, not an exhaustive list.