## Opening Checklist
AI Chef Pro
Opening Checklist — Restaurant & Bar (US example, 2026)
Phase | Task / Action | Responsible | Timing | OK | Notes
PHASE 1: BUSINESS FORMATION (months 1-2)
Legal | Choose your business structure (LLC or sole proprietorship) | Accountant | Week 1 |  | A single-member LLC is the usual pick for limited liability; a sole proprietorship is simpler but does not separate your personal and business assets. Filing fees and annual report rules vary by state
Legal | Run a business name availability search (and register a DBA if you trade under another name) | Accountant | 3-5 days |  | Check the name on your Secretary of State's website; a DBA is registered with your state or county
Legal | Open a business bank account in the company's name | Owners | 1 day |  | Fund the account with the owners' initial capital; banks usually ask for your EIN and formation documents
Legal | File the articles of organization with your Secretary of State | Attorney | 1 day |  | State filing fees vary widely; an attorney or filing service adds its own fee
Legal | Appoint a registered agent and sign the operating agreement | Accountant | 1-2 weeks |  | The operating agreement sets ownership and how decisions are made; banks and lenders may ask to see it
Tax | Get your EIN from the IRS | Accountant | 1 day |  | The EIN is free at the IRS: do not pay a site that charges for it
Tax | Get your city or county business license | Accountant | 1 day |  | Required to operate in your city or county; fees and processing times vary. Ask your accountant which classification fits a restaurant with a bar, because it can affect inspections and permits
Tax | Register for state sales tax (seller's permit) | Accountant | 1 day |  | Done with your state tax agency before your first sale; ask whether you will file quarterly or monthly. UK: VAT is 20% on hot food and on food eaten in
Payroll | Register as an employer (state withholding and unemployment insurance) | Accountant | 1-2 weeks |  | State employer account numbers for withholding and unemployment insurance
Payroll | Set up owners' draws and self-employment tax with your accountant (if applicable) | Accountant | 1 day |  | Owners of an LLC or sole proprietorship are not on payroll: they take draws and pay self-employment tax. Ask your accountant how to set it up
PHASE 2: LOCATION & PERMITS (months 2-6)
Premises | Search for and negotiate the space | Owners | 2-4 weeks |  | Confirm that restaurant use is allowed at the address before you commit
Premises | Sign the commercial lease and file the liquor license application right after (state alcohol agency + local approval) | Owners | 1 day |  | Review term, rent, NNN / CAM charges, personal guarantee and build-out allowance with an attorney. Liquor license applications usually ask for proof that you control the premises: file yours as soon as the lease is signed
Permits | Certificate of occupancy for restaurant use | City / county | 1-3 months |  | Rules and timing vary by city. Confirm that any existing certificate covers food service: a change of use may need a new one
Permits | Architect and MEP drawings for permits and health plan review | Architect / engineer | 2-4 weeks |  | Covers kitchen layout, utilities, accessibility and fire safety; the health department reviews it before you build
Permits | Building permits for the build-out (building, electrical, plumbing and gas) | City / county | 2-8 weeks |  | Needed when you alter walls, plumbing, electrical, gas or HVAC; inspections follow each stage and a final inspection closes the permit
Permits | Health permit application with your county or city health department (plan review, then inspection) | Health department | 2-4 weeks |  | Most health departments want a plan review of your layout and equipment BEFORE you build out; a restaurant gets a food establishment permit and an inspection before opening. UK: register your food business with the council at least 28 days before you start (free) and expect a Food Hygiene Rating (0-5) after inspection in England, Wales and Northern Ireland; Scotland uses FHIS (Pass / Improvement Required)
Permits | Sidewalk café / outdoor dining permit (if applicable) | City / county | 1-3 months |  | Annual renewal; fees and rules vary by city and by the area you use
Permits | Open utility accounts: electricity, water and gas | Owners | 1-2 weeks |  | Open the accounts in the company's name and ask the utility whether your kitchen needs a service upgrade (for example three-phase power)
PHASE 3: BUILD-OUT & EQUIPMENT (months 4-7)
Build-out | Renovate and fit out the space | Contractor | 4-8 weeks |  | Built to the permitted drawings: start only once the building permit is issued
Build-out | Kitchen installation: Type I hood, UL 300 suppression, gas and electrical | Installer | 2-3 weeks |  | Keep every inspection sign-off. The Type I hood and UL 300 suppression follow NFPA 96, the oven ventilation may need its own permit, and a three-phase service upgrade is arranged with the utility
Equipment | Buy and install the kitchen equipment | Owners | 2 weeks |  | See the "1. Startup Costs" tab
Equipment | Buy the dining room and bar furniture | Owners | 2 weeks
Equipment | Install the POS and restaurant software | Supplier | 1 week |  | Team training included
Equipment | Install the espresso machine and beer taps | Supplier | 1-2 days |  | Use the manufacturer's authorized service technician
Food safety | Put the full HACCP-based food safety plan in place | Consultant | 2 weeks |  | Your health department decides what must be written down; most expect documented food safety procedures
Food safety | Allergen information for every menu item (the 9 major US allergens) | Kitchen | 1 week |  | The 9 major US allergens (sesame since 2023). UK: 14
PHASE 4: STAFF (month 7)
HR | Post job openings | Owners | 2 weeks |  | Indeed, Culinary Agents, Poached and word of mouth
HR | Screening and interviews | Owners | 2 weeks |  | Prioritize restaurant experience
HR | Employment paperwork: offer letters, I-9 and W-4 | Accountant | 1 week |  | Make sure every position meets the federal minimum wage (7.25 per hour) and your state or local minimum wage, and classify each worker correctly as W-2 or 1099. Tipped staff follow special rules that differ by state
HR | Report new hires to your state (new-hire reporting) | Accountant | Before day one
HR | Team training: menu, service, food safety | Owners | 1-2 weeks |  | Before opening
HR | Food safety training for the whole team (food handler cards; certified food protection manager for the person in charge) | Owner | 1 day |  | Food handler card rules vary by state and county, and the person in charge usually needs a Certified Food Protection Manager certificate (for example ServSafe). Keep copies on file and document the training in your HACCP-based food safety plan
HR | Workplace safety basics (OSHA) and workers' compensation | Owner or outside consultant | 1 week |  | Cover the basics: training on hot equipment, slips and burns, a first-aid kit and workers' compensation insurance (required in almost every state)
PHASE 5: MARKETING & LAUNCH (months 7-8)
Brand | Design the logo, visual identity and menu | Designer | 2-3 weeks
Digital | Create a basic website + domain | Agency / DIY | 1-2 weeks
Digital | Set up your Google Business Profile + professional photos | Owners | 1 day |  | Critical for local SEO
Digital | Social media profiles: Instagram, TikTok, Facebook | Owners | 1 day
Digital | Set up online reservations (Resy, OpenTable, Google) | Owners | 1 day
Launch | Soft opening with family and friends (1 week) | Team | 1 week |  | Catch problems before you open to the public
Launch | Official grand opening + event | Team | 1 day |  | Invite the local press and local influencers
Launch | Launch the social media campaign + local Google Ads | Marketing | 1 week |  | The first 4 weeks are critical
PHASE 6: OBLIGATIONS TO CLOSE BEFORE OPENING (months 6-8)
Insurance | Buy general liability and property insurance (or a BOP), plus liquor liability if you serve alcohol | Owners | Before opening |  | It is budgeted in the workbook; this task makes sure someone actually buys it. Landlords and lenders often ask for the certificate of insurance before you open
Legal | Consumer advisory and allergen notice on the menu | Owners | 1 day |  | Your health department sets what must be displayed (for example a consumer advisory and allergen notice, or ingredient and allergen labels), and the federal and state labor law posters go in a common area. If you serve alcohol, your state liquor license and its posted notices apply: check with your state alcohol agency
Payroll | Time and payroll records for all employees (FLSA) | Accountant | From the first hire |  | Required by the FLSA (DOL); keep payroll and time records for the period that federal and state rules require
Legal | Contract with a licensed waste / grease hauler | Owners | 2 weeks |  | Inspectors check it; used cooking oil and grease cannot go down the drain
Food safety | Licensed pest control contract | Owners | 1 week |  | Part of your HACCP-based food safety plan; keep the service reports for inspections
Legal | ASCAP / BMI / SESAC licenses for background music | Owners | 2 weeks |  | ASCAP, BMI and SESAC are separate licenses: check which ones cover the music you play
Food safety | Food donation program and food waste prevention plan | Kitchen | 1 week |  | The Bill Emerson Good Samaritan Act protects donors who give surplus food in good faith. Some cities and states also have organics recycling rules: check yours
Build-out | Final inspection sign-offs for the electrical, plumbing and gas work | Installer | With the build-out |  | Without them you will not get the certificate of occupancy or the utility connections
Payroll | Complete the state new-employer registration and put up the required labor law posters | Accountant | First 30 days |  | Deadlines vary by state: check yours. The federal and state labor law posters go in a common area
Legal | Liquor license issued and posted before opening, with age-restriction signage | Owners | Start in Phase 2: often 3-12 months |  | Applied for in Phase 2, right after the lease is signed. In quota states you buy an existing license instead. Many states and insurers expect responsible beverage service training (for example TIPS or ServSafe Alcohol); post the age notice where your state says, and serve no alcohol until the license is issued
Privacy | Privacy notice and a record of how you collect and store customer data (loyalty program, email, SMS) | Owners | Before opening |  | If you text customers you need their TCPA consent first. Keep a short record of what data you collect, why and where it is stored; banks and payment processors may ask for it
Privacy | Tell the team how their time records and personal data are handled | Accountant | From the first hire |  | There is no single federal rule, but some states protect employee data: if your time clock scans fingerprints or faces, Illinois (BIPA) and a few other states require written notice and consent first. Keep payroll records secure
Privacy | Security camera signage and contract with the security company | Owners | With the build-out |  | Post notices where your state requires them; check the rules on audio recording and keep footage only as long as you need it
Privacy | Privacy notice and consent on your reservation system and email list | Owners | Before opening |  | Resy / OpenTable, SMS and newsletters collect personal data: each channel needs its own notice, and texting customers requires TCPA consent
Tax | Set up your POS to collect and report sales tax by location | Accountant | Before opening |  | Use a POS that applies the right state and local rate to each sale and reports it by location, so your sales tax returns come straight from it. Choose it before you buy the POS budgeted on the "1. Startup Costs" tab
PHASE 7: FIRST 90 DAYS (months 8-11)
Operations | Daily review of sales and food cost | Manager | Daily
Operations | Adjust the menu based on real demand | Kitchen | Monthly
Operations | Run a guest satisfaction survey | Manager | Weekly
Operations | Evaluate team performance | Manager | Monthly
Finance | Review the P&L against the forecast | Accountant | Monthly
Finance | Adjust prices if food cost drifts | Manager | Monthly
Marketing | Evaluate the ROI of the marketing campaign | Marketing | Monthly
Marketing | Ask satisfied customers for Google reviews | Team | Ongoing
AI Chef Pro · aichef.pro/en/digital-products/restaurant-business-plan
| Tasks completed: |  |  | 0 | of | 64

## Instructions
INSTRUCTIONS FOR USE
This file is part of the Restaurant Business Plan Kit by AI Chef Pro.
The GREEN cells are the editable ones: change those and the rest of the workbook recalculates on its own.
OK column: choose ✓ (done), — (pending) or N/A (not applicable). N/A items do not count toward the total.
The counter at the bottom counts only the ✓ of the whole list; N/A items come out of the total.
To edit a cell that is not green: Review → Unprotect Sheet (there is no password).
More templates and kits in the catalog at aichef.pro/en/digital-products
Designed by John Guerrero — chef and restaurant consultant since 2010, in the kitchen since age 17 · johnguerrero.es
Version 2.2 · October 2026 · aichef.pro/en/digital-products/restaurant-business-plan · info@aichef.pro
Planning tool, not financial, tax or legal advice. Requirements vary by state, county and city — check with your accountant and local authorities. This checklist is a starting point, not an exhaustive list.