## Phase 1 - Business Setup
OPENING CHECKLIST — COFFEE SHOP WITH BRUNCH
PHASE 1: BUSINESS SETUP & LEGAL STEPS
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Choose your business structure (LLC or sole proprietorship) | Accountant | Week 1 | A single-member LLC is the usual pick for limited liability; a sole proprietorship is simpler but does not separate your personal and business assets
☐ | File articles of organization with your Secretary of State | Attorney | 1-3 days | Filing fees and annual report rules vary by state. Choose your registered agent at the same time
☐ | Appoint a registered agent and sign an operating agreement | Attorney / Accountant | 1-2 weeks | The operating agreement sets ownership and how decisions are made; banks and lenders may ask to see it
☐ | Get your EIN from the IRS and register for sales tax (seller's permit) | Accountant | 1 day | The EIN is free at the IRS: do not pay a site that charges for it. Sales tax registration is done with your state tax agency, before your first sale. UK: VAT is 20% on hot food and on food eaten in; most cold takeaway food is zero-rated
☐ | Register as an employer (state withholding and unemployment insurance) | Accountant | 1 day | Registration steps and unemployment insurance rates vary by state: confirm them with your state workforce agency and your accountant before your first payroll
☐ | Open a business bank account | Owner | 1-3 days | Needed to keep personal and business finances separate; banks usually ask for your EIN and formation documents
☐ | Get your city or county business license | City / county | 1-3 days | Required to operate in your city or county; fees and processing times vary. Keep a copy on file for lenders and inspectors
☐ | Health permit application with your county or city health department (plan review, then inspection) | Health department | Variable | Most health departments want a plan review of your layout and equipment BEFORE you build out; a coffee shop with brunch gets a food establishment permit and an inspection. UK: register your food business with the council at least 28 days before you start (free) and expect a Food Hygiene Rating (1-5) after inspection in England, Wales and Northern Ireland; Scotland uses FHIS (Pass / Improvement Required)
☐ | Trademark registration (optional) | USPTO | Several months | To protect the name of your coffee shop. Check that the name is free first, and register a DBA if you trade under a name other than your LLC's
☐ | Privacy notice and a record of how you collect and store customer data (loyalty program, email, SMS) | Owner | Before opening | If you text customers you need their TCPA consent first. Keep a short record of what data you collect, why and where it is stored; banks and payment processors may ask for it
☐ | Set up your POS to collect and report sales tax by location | Accountant | Before opening | Use a POS that applies the right state and local rate to each sale and reports it by location, so your sales tax returns come straight from it. Choose it before you buy the POS budgeted on the "Startup Costs" tab
| Tasks completed: | 0 | of | 11

## Phase 2 - Location & Permits
OPENING CHECKLIST — COFFEE SHOP WITH BRUNCH
PHASE 2: LOCATION & PERMITS
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Search for and select a location | Owner | 1-3 months | Look for areas with foot traffic, offices or universities
☐ | Negotiate the commercial lease | Owner / Attorney | 1-2 weeks | Rent, term and extras (NNN / CAM charges) are negotiable. Watch for a personal guarantee, and ask for rent-free months while the build-out lasts (2-3 is a common ask)
☐ | Check zoning before you sign | City / county | Variable | Ask the city for a zoning verification BEFORE you sign the lease
☐ | Building permits for the build-out | Architect / engineer | 1-3 months | Needed when you alter walls, plumbing, electrical or HVAC. Your architect or engineer usually prepares and submits the plans
☐ | Certificate of occupancy | Architect / engineer | After final inspection | Confirm that the existing certificate covers food service; a change of use may need a new one
☐ | Sidewalk café permit (if applicable) | City / county | 1-3 months | Annual renewal; fees and rules vary by city
☐ | Sign permit (if you add or change exterior signs) | City / county | 1-3 months | Many cities require a permit and set size and lighting rules: get it before the sign maker starts
☐ | General liability insurance | Insurance agent | 1 day | Landlords and events often require 1 million per occurrence; ask your agent which limits your lease requires
☐ | Property insurance or business owner's policy (BOP) | Insurance agent | 1 day | Covers fire, theft, water damage and more; a BOP bundles liability and property coverage
☐ | Required public notices posted (health permit, labor law posters) | Owner | 1 day | Your health department sets what must be displayed, and the federal and state labor law posters go in a common area. If you serve alcohol (for example mimosas), your state liquor license and its posted notices apply: check with your state alcohol agency
☐ | Contract with a licensed waste / grease hauler | Owner | 2 weeks | Inspectors check it. Cardboard, organic waste and, if you fry, used oil, which cannot go down the drain
☐ | Licensed pest control contract | Owner | 1 week | Part of your HACCP-based food safety plan; keep the service reports for inspections
☐ | Security camera signage and contract with the security company | Owner | With the build-out | Post notices where your state requires them; check the rules on audio recording and keep footage only as long as you need it
| Tasks completed: | 0 | of | 13

## Phase 3 - Build-Out & Equipment
OPENING CHECKLIST — COFFEE SHOP WITH BRUNCH
PHASE 3: BUILD-OUT & EQUIPMENT
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Plans for permits and health plan review (architect or engineer) | Architect / engineer | 2-4 weeks | Drawings, specifications and utility layouts
☐ | Build-out: floors, walls, ceilings | Contractor | 3-6 weeks | Washable, easy-to-clean surfaces in food prep areas
☐ | Electrical work (15-20 kW service) | Electrician | 1-2 weeks | Espresso machine, oven and dishwasher are the equipment that drives the electrical load
☐ | Plumbing and drainage | Plumber | 1 week | A grease interceptor is required if you cook; check your local code
☐ | HVAC (air conditioning and heating) | Installer | 1 week | Essential for comfort, especially on an enclosed patio
☐ | Buy the professional espresso machine | Owner | 2-4 weeks | 2 groups minimum; consider an agreement with a roaster
☐ | Buy the professional grinder | Owner | 1-2 weeks | On-demand grinder, essential for quality coffee
☐ | Buy the convection / combi oven | Owner | 2-3 weeks | For pastries, hot brunch dishes and toasts
☐ | Buy refrigerated display cases | Owner | 2-3 weeks | Display for cakes, sandwiches and pastries
☐ | Buy refrigerators and a freezer | Owner | 1 week | Under-counter units plus a storage refrigerator
☐ | Buy the commercial dishwasher | Owner | 1-2 weeks | 2-3 minute cycle, essential at volume
☐ | Dining room and counter furniture | Carpenter / Supplier | 3-4 weeks | Style that matches the concept and is comfortable for a long brunch
☐ | Patio furniture + awning / umbrellas | Supplier | 2-3 weeks | Check your city's rules for sidewalk and patio seating
☐ | POS and software installation | Supplier | 1 week | Link orders, payments and inventory
☐ | Decor and lighting | Interior designer | 2-3 weeks | Warm lighting, plants and a spot made for photos
| Tasks completed: | 0 | of | 15

## Phase 4 - Staff
OPENING CHECKLIST — COFFEE SHOP WITH BRUNCH
PHASE 4: STAFF & TRAINING
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Define the org chart and shifts | Owner | 1 week | Coffee shop: two 8-hour shifts that overlap at midday, for example 7 am-3 pm and 12 pm-8 pm (13 hours open, as on the Staffing tab)
☐ | Post job openings | Owner | 1-2 weeks | Look for baristas with specialty coffee experience
☐ | Screening and interviews | Owner | 2 weeks | Practical test: pull an espresso and pour a latte art
☐ | Employment paperwork: offer letters, I-9 and W-4 | Accountant | 1 day | Make sure every position meets the federal minimum wage ($7.25 per hour) and your state or local minimum wage, and classify each worker correctly as W-2 or 1099
☐ | Report new hires to your state (new-hire reporting) | Accountant | Per state deadline | Check your state's deadline; set up payroll withholding before the first paycheck
☐ | Food safety training for the whole team (food handler cards; certified food protection manager for the person in charge) | Owner | 1 day | Food handler card rules vary by state and county, and the person in charge usually needs a Certified Food Protection Manager certificate (for example ServSafe). Keep copies on file and document the training in your HACCP-based food safety plan
☐ | Workplace safety basics (OSHA) and workers' compensation | Owner or outside consultant | 1-2 weeks | Cover the basics: training on hot equipment, slips and burns, a first-aid kit and workers' compensation insurance (required in almost every state)
☐ | Barista and coffee training | Owner / Trainer | 1-2 weeks | Standardize shots, recipes and machine cleaning
☐ | Allergen and food safety training (9 major US allergens) | Owner | 1 day | Plant milks (soy, almond), wheat, tree nuts and sesame: critical at brunch. UK: 14 allergens
☐ | Customer service training | Owner | 1 day | Service standards, complaints and suggested selling
☐ | Time and payroll records for all employees (FLSA) | Accountant | From the first hire | Required by the FLSA (DOL); keep payroll and time records for the period that federal and state rules require
☐ | Tell the team how their time records and personal data are handled | Accountant | From the first hire | There is no single federal rule, but some states protect employee data: if your time clock scans fingerprints or faces, Illinois (BIPA) and a few other states require written notice and consent first. Keep payroll records secure
| Tasks completed: | 0 | of | 12

## Phase 5 - Marketing
OPENING CHECKLIST — COFFEE SHOP WITH BRUNCH
PHASE 5: MARKETING & LAUNCH
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Design your visual identity: logo, colors and typography | Designer | 2-3 weeks | Consistent style: rustic, modern, specialty...
☐ | Create a basic website | Designer / Developer | 1-2 weeks | Your Google Business Profile is more urgent than the website
☐ | Google Business Profile (CRITICAL) | Owner | 1 day | Category: Coffee shop. Take care with the photos, hours and menu
☐ | Social media profiles (Instagram first) | Owner | 1 day | Instagram is the #1 channel for coffee shops and brunch spots
☐ | Professional photo shoot | Photographer | 1 day | Photos of brunch dishes, latte art and the atmosphere
☐ | Design the menu and the bar chalkboard | Designer | 1 week | Printed menu, bar chalkboard and a digital menu with a QR code
☐ | Exterior sign + window vinyl | Sign maker | 1 week | First impression from the street: essential
☐ | Pre-opening social media campaign | Owner | 2-4 weeks | Countdown, behind-the-scenes content and an opening giveaway
☐ | Coffee supplier agreements | Owner | 2 weeks | Consider a local roaster: a brand differentiator
☐ | Register on Google Maps and Yelp | Owner | 1 day | Also Resy / OpenTable if your brunch takes reservations
☐ | Grand opening event | Owner | 1 day | Invite neighbors, local influencers and the neighborhood press
☐ | Loyalty program | Owner | 1 week | Punch card with the tenth coffee free, or a points app
☐ | ASCAP / BMI / SESAC licenses for background music | Owner | 2 weeks | ASCAP, BMI and SESAC are separate licenses: check which ones cover the music you play
☐ | Privacy notice and consent on your reservation system and email list | Owner | Before opening | Resy / OpenTable, SMS and newsletters collect personal data: each channel needs its own notice, and texting customers requires TCPA consent
| Tasks completed: | 0 | of | 14

## Phase 6 - First 90 Days
OPENING CHECKLIST — COFFEE SHOP WITH BRUNCH
PHASE 6: FIRST 90 DAYS
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Daily review of cash and sales | Owner | Daily | Compare with the projections in the financial plan
☐ | Weekly food cost check | Owner | Weekly | Weigh and measure: coffee, milk, brunch ingredients
☐ | Adjust the menu based on real sales | Owner | Month 1 | Drop what does not sell, push the bestsellers
☐ | Customer surveys (in person + Google) | Owner | Month 1-3 | Ask for Google reviews and reply to ALL of them
☐ | Optimize staff schedules | Owner | Month 1-2 | Reinforce the morning peak, cut the dead hours in the afternoon
☐ | Review suppliers and negotiate prices | Owner | Month 2 | With real volume, renegotiate coffee, milk and pastries
☐ | Launch delivery if there is demand | Owner | Month 2-3 | DoorDash / Uber Eats for brunch takeout
☐ | Analyze local competition | Owner | Month 1 | Visit other coffee shops in the area and compare
☐ | First quarter close and first sales tax return | Accountant | Month 3 | Compare actual P&L against the financial plan
☐ | Corrective action plan | Owner | Month 3 | If variance is over 15%, review costs and strategy
| Tasks completed: | 0 | of | 10

## Instructions
INSTRUCTIONS FOR USE
This file is part of the Coffee Shop Business Plan Kit by AI Chef Pro.
The GREEN cells are the editable ones: change those and the rest of the workbook recalculates on its own.
OK column: choose ✓ (done), ☐ (pending) or N/A (not applicable). N/A items do not count toward the total.
Each tab's counter counts only the ✓; N/A items come out of the total.
To edit a cell that is not green: Review → Unprotect Sheet (there is no password).
More templates and kits in the catalog at aichef.pro/en/digital-products
Designed by John Guerrero — chef and restaurant consultant since 2010, in the kitchen since age 17 · johnguerrero.es
Version 2.2 · October 2026 · aichef.pro/en/digital-products/coffee-shop-business-plan · info@aichef.pro
Planning tool, not financial, tax or legal advice. Requirements vary by state, county and city — check with your accountant and local authorities. This checklist is a starting point, not an exhaustive list.