## Phase 1 - Business Setup
FOOD TRUCK STARTUP CHECKLIST
PHASE 1: BUSINESS SETUP & REGISTRATIONS
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Choose your legal structure (LLC or sole proprietorship) | Accountant | Week 1 | A sole proprietorship can work if you start alone; an LLC separates personal and business liability and suits partners. Ask your accountant about S or C corporations.
☐ | Form your LLC (articles of organization, registered agent, operating agreement) | Attorney / Accountant | 1 day to 4 weeks | Skip this step if you operate as a sole proprietor. Filing fees and processing times vary by state; write an operating agreement even for a single-member LLC.
☐ | Get your EIN (IRS) and register for state sales tax (seller's permit) | Accountant | 1 day | The EIN is free from the IRS and you need one if you have employees or a multi-member LLC. Register for sales tax with your state before your first sale and ask whether you file monthly or quarterly. Keep a resale certificate for tax-free purchases of items you resell.
☐ | Register as an employer (state withholding, unemployment insurance and workers' comp) | Accountant | 1 day | Registration steps and unemployment insurance rates vary by state: confirm them with your state workforce agency and your accountant before your first payroll
☐ | City or county business license | City / county | 1-3 days | Required in most cities, and some issue it online. If you trade under another name, file a DBA. The mobile vending license comes in Phase 2.
☐ | Open a business bank account | Owner | 1-3 days | Keep business and personal money separate
☐ | Health permit application with your county or city health department (plan review, then inspection) | Health department | Variable | For a food truck the permit is the mobile food unit permit, which comes after plan review (see Phase 2). Ask your county or city health department what it needs before you build. UK: register your food business with the council at least 28 days before you start (free; use the council where the vehicle is kept).
☐ | General liability insurance | Insurance agent | 1 day | Events and landlords often require 1M per occurrence. Ask your insurance agent for certificates of insurance, which events will ask you to provide.
☐ | Commercial auto insurance (truck or trailer) | Insurance agent | 1 day | Comprehensive and collision coverage recommended
☐ | Privacy notice and a record of how you collect and store customer data (loyalty program, email, SMS) | Owner | Before opening | Collecting emails, phone numbers or text consent for a loyalty program brings privacy duties: post a simple privacy notice, get TCPA consent before you text, and keep a record of what you collect and where it is stored. Covers loyalty members, staff and suppliers.
☐ | Set up your POS to collect and report sales tax by location | Accountant | Before opening | A truck often sells in several cities or counties with different rates. Choose a POS that applies the right rate by location and exports reports for your sales tax return, before you buy the tablet and card reader budgeted on the Startup Costs tab: switching later is expensive.
| Tasks completed: | 0 | of | 11

## Phase 2 - Truck & Permits
FOOD TRUCK STARTUP CHECKLIST
PHASE 2: TRUCK & PERMITS
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Select and buy the truck | Owner | 2-6 weeks | Step van, trailer or truck, new or used. Have a mechanic inspect any used unit, and check its GVWR: it decides whether you need a CDL (see below).
☐ | Build out the truck for cooking | Specialized truck builder | 4-8 weeks | Service window, counter, plumbing and electrical installations. The layout has to match the plans you submit to the health department.
☐ | Propane system inspection and fire marshal sign-off (if you cook with propane) | Installer / fire marshal | 1 week | Many cities send the fire marshal before the health inspection (propane, extinguishers, suppression); NFPA 96 applies where adopted. Re-inspection is often annual.
☐ | DMV registration and title | DMV | 1 day | Register the vehicle in the state where you will keep it. Bring the title or bill of sale and proof of insurance; some states require an inspection after structural modifications.
☐ | Health plan review and drawings | Architect / engineer | 2-3 weeks | Equipment layout, workflow and water tank drawings: most health departments review them before you build.
☐ | Mobile food unit permit and health inspection | Health department | 2-4 weeks | Inspection of the finished, equipped truck. UK: the council inspects and gives you a Food Hygiene Rating (1-5) in your first months in England, Wales and Northern Ireland; Scotland uses FHIS (Pass / Improvement Required).
☐ | City mobile vending license (one per city) | City / county | 1-3 months | Every city has its own rules. A license is not transferable between cities and each truck needs its own. UK: street trading licence or consent from each council where you sell.
☐ | Parking and vending-zone rules; written permission for private property | City / county | 2-8 weeks | If you plan a fixed spot: check the designated vending zones and time limits, or get the property owner's written permission.
☐ | Apply to markets and events (temporary food event permits) | Organizers | Variable | Many markets keep waitlists, and events often require a temporary food permit for each date.
☐ | Driver's license class (CDL at 26,001 lb GVWR or more, or for a heavy truck-and-trailer combination) | Owner | Variable | Federal rule (49 CFR 383.91): a CDL is required for a single vehicle rated 26,001 lb GVWR or more, or for a combination rated 26,001 lb or more when the trailer is rated over 10,000 lb (Class A). Below that, most trucks need only a regular license; check with your state DMV, which may add its own rules.
☐ | Commissary agreement signed and a copy on file | Owner | 1 day | Most health departments require a signed agreement with a licensed commissary for water, waste dumping, food storage and cleaning. Keep a copy on the truck for inspections.
☐ | Contract with a licensed grease / waste hauler | Owner | 2 weeks | Often handled at the commissary: ask what it provides. Used fryer oil needs a licensed collector, and the arrangement may be checked in the truck's health inspection.
☐ | Licensed pest control contract | Owner | 1 week | Usually arranged through the commissary. Keep the service reports for health inspections and for your HACCP-based food safety plan (Phase 4).
| Tasks completed: | 0 | of | 13

## Phase 3 - Equipment
FOOD TRUCK STARTUP CHECKLIST
PHASE 3: EQUIPMENT & SETUP
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Griddle (propane or electric) | Supplier | 1-2 weeks | Match it to your concept: burgers, crepes, tacos
☐ | Fryer (if you need one) | Supplier | 1 week | With a filter and a plan for used oil
☐ | Exhaust hood with filters | Installer | 1-2 weeks | Needed over cooking equipment that produces grease-laden vapor. Check your local fire code (NFPA 96 where adopted).
☐ | Compact refrigerator / freezer | Supplier | 1 week | 12V or 120V depending on the generator
☐ | Quiet generator | Supplier | 1 week | 5-7 kW minimum, quiet (below 70 dB)
☐ | Fresh water and gray water tanks | Installer | 1 week | Tank sizes are set by your county: check your county's minimum fresh and gray water tank sizes (in gallons) with the health department before you build. Gray water usually has to exceed fresh water.
☐ | Dish sink (two or three compartments) and handwashing sink | Installer | With the build-out | Required by the health code. Confirm how many compartments your county wants.
☐ | Mobile POS and 4G card reader | Supplier | 1 week | Tablet and card reader with a 4G connection
☐ | Smallwares and kitchen utensils | Supplier | 1 week | Sized for a very small space
☐ | Compostable packaging | Supplier | 1 week | Some cities require compostable or recyclable packaging and restrict foam: check yours.
☐ | Full truck wrap | Sign maker | 1-2 weeks | First impression: your brand must be visible from a distance
☐ | Awning, folding tables and banners | Supplier | 1 week | A quick-setup kit for every service
| Tasks completed: | 0 | of | 12

## Phase 4 - Staff
FOOD TRUCK STARTUP CHECKLIST
PHASE 4: STAFF & TRAINING
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Define the minimum crew (2-3 people) | Owner | 1 week | Owner plus at least one helper
☐ | Hire a helper (if applicable) | Accountant | 1-2 weeks | W-2 employee or 1099 contractor? Misclassifying is risky: ask your accountant. New hires need an I-9 and W-4, and your state may require new-hire reporting.
☐ | Food safety training for the whole team (food handler cards; certified food protection manager for the person in charge) | Owner | 1 day | Requirements vary by state: many require food handler cards for staff, and the person in charge usually needs a Certified Food Protection Manager certificate (for example ServSafe). Keep copies of the certificates on the truck.
☐ | Train the team on your HACCP-based food safety plan | Owner | 1 day | Temperatures, the cold chain on the truck and traceability
☐ | Food truck operations training | Owner | 1 week | Setup, fast service, breakdown and cleaning
☐ | OSHA basics and workplace safety plan | Owner or outside consultant | 1-2 weeks | Specific hazards: propane, hot oil, tight space
☐ | Allergen protocol | Owner | 1 day | Know the 9 major US allergens (sesame since 2023; UK: 14) and post a visible allergen notice at the service window
☐ | Full setup and breakdown rehearsal | Team | 1 day | Time it: aim for under 30 minutes to set up
☐ | Time and payroll records for all employees (FLSA) | Accountant | From the first hire | The FLSA requires accurate records of hours worked and pay. They apply from the first hire, even part time; check your state's retention rules.
☐ | Tell the team how their time records and personal data are handled | Accountant | From the first hire | There is no single federal rule, but some states protect employee data: if your time clock scans fingerprints or faces, Illinois (BIPA) and a few other states require written notice and consent first. Keep payroll records secure
| Tasks completed: | 0 | of | 10

## Phase 5 - Marketing
FOOD TRUCK STARTUP CHECKLIST
PHASE 5: MARKETING & LAUNCH
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Create your visual identity and brand | Designer | 2-3 weeks | Logo, colors, truck wrap, branded packaging
☐ | Set up your Google Business Profile | Owner | 1 day | Category: Food truck. Photos and locations
☐ | Social media profiles (Instagram + TikTok) | Owner | 1 day | A video of the truck and the food has viral potential
☐ | Website with your location calendar | Developer | 1-2 weeks | Where you will be each day of the week
☐ | Professional photo and video shoot | Photographer | 1 day | Food in action, the wrapped truck, service
☐ | Agreements with markets and events | Owner | 2-4 weeks | Weekly markets mean recurring income
☐ | Sign up on food truck apps | Owner | 1 day | Roaming Hunger, StreetFoodFinder and local street food apps
☐ | Agreements with offices and companies | Owner | 2 weeks | Corporate lunches bring recurring orders
☐ | Grand opening event | Owner | 1 day | First service with a promo: buy one get one, social media, local influencers
☐ | Mobile loyalty program | Owner | 1 week | Digital card or QR code: the tenth meal is free
☐ | Music licenses (ASCAP / BMI / SESAC) if you play music at events and festivals | Owner | Before you play music | Ask the organizer: a festival's license may cover the venue but not each vendor's own speaker.
☐ | Privacy notice and consent for the QR loyalty program (TCPA consent for SMS) | Owner | Before opening | A QR loyalty program collects contact details: post a privacy notice up front, and get consent before you send marketing texts (TCPA).
| Tasks completed: | 0 | of | 12

## Phase 6 - First 90 Days
FOOD TRUCK STARTUP CHECKLIST
PHASE 6: FIRST 90 DAYS
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Test locations (at least 5) | Owner | Month 1 | Measure sales by location and day of the week
☐ | Daily sales log by location | Owner | Daily | Learn which locations work and which do not
☐ | Weekly food cost check | Owner | Weekly | Weigh ingredients, track waste and adjust your orders
☐ | Adjust the menu based on sales | Owner | Month 1 | Drop slow items, push bestsellers
☐ | Optimize your weekly route | Owner | Month 1-2 | Lock in your best days and locations as a fixed route
☐ | Customer surveys and Google / Yelp reviews | Owner | Month 1-3 | Ask for reviews and answer every one
☐ | Evaluate events and festivals | Owner | Month 2 | Festivals can multiply a normal day's sales: track them separately
☐ | Renegotiate with suppliers | Owner | Month 2 | With real volume, ask for better prices
☐ | First quarter close and first sales tax return | Accountant | Month 3 | Compare actual P&L against the financial plan
☐ | Expansion plan (second truck or brick-and-mortar location) | Owner | Month 3 | If it works, evaluate a second truck or a fixed location
| Tasks completed: | 0 | of | 10

## Instructions
INSTRUCTIONS FOR USE
This file is part of the Food Truck Business Plan Kit by AI Chef Pro.
The GREEN cells are the editable ones: change those and the rest of the workbook recalculates on its own.
OK column: choose ✓ (done), ☐ (pending) or N/A (not applicable). N/A items do not count toward the total.
Each tab's counter counts only the ✓; N/A items come out of the total.
To edit a cell that is not green: Review → Unprotect Sheet (there is no password).
More templates and kits in the catalog at aichef.pro/en/digital-products
Designed by John Guerrero — chef and restaurant consultant since 2010, in the kitchen since age 17 · johnguerrero.es
Version 2.2 · October 2026 · aichef.pro/en/digital-products/food-truck-business-plan · info@aichef.pro
Planning tool, not financial, tax or legal advice. Requirements vary by state, county and city — check with your accountant and local authorities. This checklist is a starting point, not an exhaustive list.