## Instructions
06 · Catering Event Checklists: Weddings, Corporate, Cocktail Receptions & Outdoor
How to use this template:
▸ Checklists adapted to each type of catering event.
▸ Weddings, corporate events, cocktail receptions and outdoor events.
▸ Use the tab for the type of event you have coming up.
Customization:
▸ Every event has its own quirks. Use these lists as a base.
▸ Combine them with the general checklists (01-05) for full coverage.
Designed by John Guerrero — chef and restaurant consultant since 2010, in professional kitchens since age 17 · johnguerrero.es
Version 2.0 · October 2026 · aichef.pro/en/digital-products/catering-checklist-templates · info@aichef.pro

## Weddings
Wedding — Specific Checklist
AI Chef Pro · aichef.pro — Catering Checklists Kit Pro
Pre-Wedding (Week Before)
# | Task | Area | Assigned to | ✓ | Time | Notes
1 | Confirm with the wedding planner the guaranteed count already locked by 15 days out; any later change only as your contract allows | Office
2 | Confirm the table layout and the seating chart | Office
3 | Check the kids' menu and the number of children | Office
4 | Collect each guest's allergies and intolerances IN WRITING and mark them on the seating chart; settle the alternative dishes with the kitchen and who serves them | Office
5 | Confirm the schedule: cocktail hour, dinner, open bar, cake | Office
6 | Coordinate access and timing with the florist, DJ and photographer | Office
7 | Prepare the wedding cake or coordinate with an outside bakery | Production
Wedding Day
# | Task | Area | Assigned to | ✓ | Time | Notes
1 | Welcome cocktail hour: timing, canapes, drinks | Service
2 | Table service: coordinate the courses with the wedding protocol | Service
3 | Cake cutting: coordinate with the photographer and DJ | Service
4 | Open bar: control the start and end times; ID anyone who looks under 30 (21+) and don't serve anyone visibly intoxicated; operate under the license your state requires (the caterer's or the venue's) | Service
5 | Late-night snack service (if applicable) | Service
6 | Make sure the couple and the head table are looked after at all times | Service
| Tasks done: | 0 | of | 13
Signed off by: _________________ Date: ___/___/______
© 2026 AI Chef Pro · aichef.pro

## Corporate
Corporate Event — Checklist
AI Chef Pro · aichef.pro — Catering Checklists Kit Pro
Pre-Event
# | Task | Area | Assigned to | ✓ | Time | Notes
1 | Confirm with the company: event agenda, coffee breaks, meals | Office
2 | Check the AV requirements: projector, screen, microphone, podium | Office
3 | Plan the coffee breaks: morning and afternoon, with variety | Production
4 | Confirm attendees' allergies, intolerances and special diets IN WRITING, and pass them to the kitchen and the service team | Office
5 | Coordinate setup access with the hotel / venue | Office
During the event
# | Task | Area | Assigned to | ✓ | Time | Notes
1 | Morning coffee break: serve at the exact agreed time | Service
2 | Lunch: service per format (buffet, plated, boxed) | Service
3 | Afternoon coffee break: refill and vary the offer vs. the morning | Service
4 | Keep the water, coffee and snack station stocked all day | Service
5 | Networking cocktail hour: set up quickly after the final session | Service
| Tasks done: | 0 | of | 10
Signed off by: _________________ Date: ___/___/______
© 2026 AI Chef Pro · aichef.pro

## Cocktail Reception
Cocktail Reception / Standing — Checklist
AI Chef Pro · aichef.pro — Catering Checklists Kit Pro
Preparation
# | Task | Area | Assigned to | ✓ | Time | Notes
1 | Work out the ratio: 12–15 pieces per person for a 2-hour cocktail reception | Production
2 | Prepare canape trays with variety: seafood, meat, vegetable | Production
3 | Prep the action stations: ceviche, tartare, wok | Production
4 | Ceviche, tartare and any fish served raw or undercooked — parasite destruction: use only fish with documented freezing (−4 °F or below for 7 days, or −31 °F or below until solid + 15 h; FDA Food Code 3-402.11), keep the record 90 days and note the lot; put the raw/undercooked consumer advisory on the station sign or menu (FDA Food Code 3-603.11) | Production
5 | Every server must know the allergens on the tray they pass: an allergen card per tray, reviewed at the pre-event briefing. US: the 9 major allergens (FALCPA + FASTER Act: milk, egg, fish, crustacean shellfish, tree nuts, peanuts, wheat, soy and sesame); UK: 14 | Service
6 | Set up a cocktail bar with 3–4 options + soft drinks + water, only under the alcohol license your state requires (or the venue's); 21+ with ID | Setup
7 | Work out staffing: 1 server per 20 guests for passed trays | Office
During the Cocktail Reception
# | Task | Area | Assigned to | ✓ | Time | Notes
1 | Send out trays every 10–15 min, rotating the offer | Service
2 | Refill the action stations to match the pace of consumption | Service
3 | Watch the flow of drinks: don't leave anyone without a glass | Service
4 | Continuously collect used glassware and napkins | Service
5 | Keep the areas clean and presentable throughout the event | Cleaning
| Tasks done: | 0 | of | 12
Signed off by: _________________ Date: ___/___/______
© 2026 AI Chef Pro · aichef.pro

## Outdoor Events
Outdoor Event — Checklist
AI Chef Pro · aichef.pro — Catering Checklists Kit Pro
Outdoor Logistics
# | Task | Area | Assigned to | ✓ | Time | Notes
1 | Check the weather forecast 72 h, 24 h and 2 h before | Office
2 | Confirm a rain plan B (tent, indoors, alternate date) | Office
3 | Check vehicle access to the site and the unloading area | Transport
4 | Check the power supply: generator or the venue's hookup | Office
5 | Locate the nearest potable water source and provide a handwashing station (hot water, soap, paper towels and a catch bucket, as your health department requires) | Office
6 | Set up a tent or canopy for the kitchen and service area if needed; large tents often need a fire marshal permit and flame-resistant fabric: ask your city | Setup
Outdoor Food Safety
# | Task | Area | Assigned to | ✓ | Time | Notes
1 | Protect food from direct sun and ambient heat | Production
2 | Double the temperature checks: outdoors, food warms up much faster. Hold hot food at 135 °F or above and cold food at 41 °F or below. Food without temperature control falls under time as a public health control (FDA Food Code 3-501.19): mark the time it came out of temperature control and serve it within 4 h; whatever is left at 4 h is discarded, and it can't go back into hot or cold holding to restart the clock. Cold food can go up to 6 h only if it came out at 41 °F or below and you check it never passes 70 °F: discard it as soon as it does, and at 6 h. This needs a written procedure and, depending on your county, notice to the health department. In hot weather, refill more often and in smaller amounts | Production
3 | Use covered display cases or film to protect from insects | Service
4 | Cut exposure time: refill more often, in smaller quantities | Service
5 | Keep extra ice and insulated carriers as backup | Production
6 | Check the lighting if the event runs into the night | Office
| Tasks done: | 0 | of | 12
Signed off by: _________________ Date: ___/___/______
© 2026 AI Chef Pro · aichef.pro