## Phase 1 - Business Setup
OPENING CHECKLIST — BAKERY
PHASE 1: BUSINESS SETUP
OK | TASK | RESPONSIBLE | TIMING | NOTES
☐ | Choose a business structure (LLC or sole proprietorship) | Accountant | Week 1 | An LLC is formed by filing articles of organization with your Secretary of State; ask your accountant which structure fits you (self-employment tax, owners' draws)
☐ | File articles of organization and sign the operating agreement | Attorney | 1-3 days
☐ | EIN and state sales tax registration (seller's permit) | Accountant | 1 day | Get your EIN (free from the IRS) and register for sales tax with your state. A bakery that sells to the public (retail) and to other businesses (wholesale) handles the two channels differently: ask a café that resells your bread for its resale certificate and keep a copy on file, and confirm with your accountant how your state treats each channel
☐ | Register as an employer (state withholding and unemployment insurance) | Accountant | 1 day | Registration steps and unemployment insurance rates vary by state: confirm them with your state workforce agency and your accountant before your first payroll
☐ | City or county business license | City / county | 1-3 days
☐ | Business bank account | Owner | 1-3 days
☐ | Health permit application with your county or city health department (plan review, then inspection) | Health department | Variable | A health department plan review comes first, then the food establishment permit and an inspection before you open. Depending on the state, the health department (sales to the public) or the state agriculture department (production and wholesale) issues the license. A cottage food law lets you sell certain foods made at home with limits on channel and sales: this kit is for a commercial bakery with a storefront, so the commercial kitchen license applies. FDA food facility registration is needed only if wholesale becomes your main channel; if it grows beyond occasional deliveries, check with your accountant and your state agency
☐ | General liability insurance | Insurance agent | 1 day | Landlords and events often require 1 million per occurrence
☐ | Trademark (optional) | USPTO | 4-6 months
☐ | Privacy notice and a record of how you collect and store customer data (loyalty program, email, SMS) | Owner | Before opening | Cover the data you collect from customers (loyalty program, email list), staff and suppliers (mills, distributors): post a privacy notice and get consent for marketing messages (TCPA consent for SMS)
☐ | Set up your POS to collect and report sales tax by location | Accountant | Before opening | Set up your POS to collect and report sales tax by location. Do it before you buy the POS + scale budgeted on the "Startup Costs" tab, and remember that wholesale accounts need invoices and a resale certificate on file
| Tasks completed: | 0 | of | 11

## Phase 2 - Location & Permits
OPENING CHECKLIST — BAKERY
PHASE 2: LOCATION & PERMITS
OK | TASK | RESPONSIBLE | TIMING | NOTES
☐ | Site search (storefront + production area) | Owner | 1-3 months | Plan for about 860 sq ft or more: production area + storefront + storage
☐ | Commercial lease review | Attorney | 1-2 weeks | Review NNN / CAM charges and any personal guarantee; ask for 2-3 months of free rent during the build-out
☐ | Zoning check | City / county | Variable | Confirm the permitted use (retail bakery / light food manufacturing) BEFORE you sign
☐ | Certificate of occupancy (bakery with ovens) | Architect / engineer | 2-4 months | A bakery with ovens counts as food production, not just retail: ask the city which use applies
☐ | Architect + MEP drawings (oven ventilation, electrical load) | Architect / engineer | 2-4 weeks | Critical: ovens draw a lot of power, and the utility may need to upgrade the service (three-phase)
☐ | Building, electrical, plumbing and gas permits | City / county | 1-3 months | Needed for a major renovation; schedule the final inspections
☐ | Property insurance or business owner's policy (BOP) | Insurance agent | 1 day | Fire risk from the ovens is the key point: tell your agent
☐ | Electric service upgrade (three-phase, check with your utility) | Utility | 2-4 weeks | High load: ovens plus walk-in cooler, so ask the utility early about timing and cost
☐ | Ingredient and allergen labels for packaged and wholesale products | Owner | 1 day | Your health department sets what must be displayed (for example a consumer advisory and allergen notice, or ingredient and allergen labels), and the federal and state labor law posters go in a common area. If you serve alcohol, your state liquor license and its posted notices apply: check with your state alcohol agency
☐ | Contract with a licensed waste / grease hauler | Owner | 2 weeks | It is often checked at inspection. Cardboard and organic waste (dough and production scraps); this plan does not fry, so there is no used cooking oil to manage
☐ | Licensed pest control contract | Owner | 1 week | Hire a licensed pest control company; the service record is part of your HACCP-based food safety plan. Stored flour is a common pest magnet: do not leave it until after you open
☐ | Security camera signage and contract with the security company | Owner | With the build-out | Post notices where your state requires them; check the rules on audio recording and keep footage only as long as you need it
| Tasks completed: | 0 | of | 12

## Phase 3 - Equipment
OPENING CHECKLIST — BAKERY
PHASE 3: EQUIPMENT
OK | TASK | RESPONSIBLE | TIMING | NOTES
☐ | Deck or rack oven | Supplier | 4-8 weeks | Deck = artisan bread, rack = volume
☐ | Spiral mixer (55-110 lb) | Supplier | 2-3 weeks | Capacity based on daily production
☐ | Divider-rounder | Supplier | 2-3 weeks | Batch production
☐ | Proofer / retarder (controlled fermentation) | Supplier | 3-4 weeks | Programmable overnight slow fermentation
☐ | Walk-in cooler and freezer | Supplier | 2 weeks | Ingredient storage + frozen dough
☐ | Dough sheeter (for pastries) | Supplier | 2-3 weeks | Croissants, puff pastry
☐ | Stainless table + production shelving | Supplier | 1-2 weeks | Enough work surface
☐ | Exhaust + hood + fan | Installer | 1-2 weeks | Required
☐ | Display case | Supplier | 2 weeks | Bread and pastries of the day
☐ | Store counter + register | Carpenter | 2-3 weeks
☐ | POS + scale | Supplier | 1 week
☐ | Trays, molds, utensils | Supplier | 1 week
| Tasks completed: | 0 | of | 12

## Phase 4 - Staff
OPENING CHECKLIST — BAKERY
PHASE 4: STAFF
OK | TASK | RESPONSIBLE | TIMING | NOTES
☐ | Define the org chart and shifts | Owner | 1 week | The early production shift (4-5 AM) is critical
☐ | Hire a head baker | Owner | 2-4 weeks | Experience with sourdough and slow fermentation
☐ | Employment paperwork: offer letters, I-9 and W-4 | Accountant | 1 day | Make sure every position meets the federal minimum wage (7.25 per hour) and your state or local minimum wage, and classify each worker correctly as W-2 or 1099
☐ | Report new hires to your state (new-hire reporting) | Accountant | Per state deadline
☐ | Food safety training for the whole team: food handler cards and a Certified Food Protection Manager (for example ServSafe). The rules vary by state and county; keep copies on file and document the training in your HACCP-based food safety plan | Owner | 1 day
☐ | Workplace safety basics (OSHA) for ovens, heavy loads and the early shift, plus workers' compensation | Owner or outside consultant | 1-2 weeks | Specific hazards: burns, flour dust in the air
☐ | Sourdough and fermentation training | Head baker | 1-2 weeks | Standardize: times, temperatures, dough hydration
☐ | HACCP-based food safety training for the bakery | Owner | 1 day | Wheat is the central allergen in a bakery, along with milk, eggs, tree nuts and sesame: know the 9 major US allergens (UK: 14) and keep flour traceability
☐ | Time and payroll records for all employees (FLSA) | Accountant | From the first hire | Required by the FLSA (DOL); keep payroll and time records for the period that federal and state rules require. Especially relevant with the head baker's early shift
☐ | Tell the team how their time records and personal data are handled | Accountant | From the first hire | There is no single federal rule, but some states protect employee data: if your time clock scans fingerprints or faces, Illinois (BIPA) and a few other states require written notice and consent first. Keep payroll records secure
| Tasks completed: | 0 | of | 10

## Phase 5 - Marketing
OPENING CHECKLIST — BAKERY
PHASE 5: MARKETING
OK | TASK | RESPONSIBLE | TIMING | NOTES
☐ | Brand identity | Designer | 2-3 weeks | Artisan, rustic or modern style
☐ | Google Business Profile | Owner | 1 day | Category: Bakery. Photos of fresh-baked bread
☐ | Instagram | Owner | 1 day | Photos of sourdough, the process and fresh batches
☐ | Basic website | Developer | 1-2 weeks | With hours, menu and wholesale orders
☐ | Professional photos | Photographer | 1 day | Bread coming out of the oven, crumb, crust, the bakery
☐ | Wholesale agreements with cafés and restaurants | Owner | 2-4 weeks | Wholesale: recurring revenue
☐ | Signage | Sign maker | 1 week
☐ | Grand opening | Owner | 1 day | Free bread and coffee tasting
☐ | Loyalty card | Owner | 1 week | The 10th loaf, free
☐ | ASCAP / BMI / SESAC music licenses if you play music in the shop | Owner | 2 weeks | They are separate licensing organizations: if you play music in the shop, you may need to pay more than one
☐ | Privacy notice and consent for the email list and in agreements with wholesale accounts | Owner | Before opening | Text messages (TCPA consent for SMS), the newsletter and the contact details of your wholesale accounts all involve personal data: each channel needs its own notice and consent
| Tasks completed: | 0 | of | 11

## Phase 6 - First 90 Days
OPENING CHECKLIST — BAKERY
PHASE 6: FIRST 90 DAYS
OK | TASK | RESPONSIBLE | TIMING | NOTES
☐ | Track daily production (lb) | Head baker | Daily | Match production to real demand
☐ | Track unsold bread waste | Owner | Daily | Target: under 8% waste
☐ | Weekly food cost | Owner | Weekly | Watch flour, butter and chocolate
☐ | Adjust the menu | Owner | Month 1 | Push what sells best
☐ | Optimize the production schedule | Head baker | Month 1 | Have fresh bread at 7:30 am and 5:00 pm
☐ | Google reviews | Owner | Month 1-3 | Ask for them and answer every one
☐ | Evaluate the wholesale channel | Owner | Month 2 | Cafés and restaurants = steady volume
☐ | Renegotiate flour suppliers | Owner | Month 2 | With real volume
☐ | Quarter close and first sales tax return | Accountant | Month 3 | Actual P&L vs plan
☐ | Evaluate a second production shift | Owner | Month 3 | If demand grows: an afternoon shift for pastries
| Tasks completed: | 0 | of | 10

## Instructions
INSTRUCTIONS FOR USE
This file is part of the Bakery Business Plan Kit by AI Chef Pro.
The GREEN cells are the editable ones: change those and the rest of the workbook recalculates on its own.
OK column: choose ✓ (done), ☐ (pending) or N/A (not applicable). N/A items do not count toward the total.
Each tab's counter counts only the ✓; N/A items come out of the total.
To edit a cell that is not green: Review → Unprotect Sheet (there is no password).
More templates and kits in the catalog at aichef.pro/en/digital-products
Designed by John Guerrero — chef and restaurant consultant since 2010, in the kitchen since age 17 · johnguerrero.es
Version 2.2 · October 2026 · aichef.pro/en/digital-products/bakery-business-plan · info@aichef.pro
Planning tool, not financial, tax or legal advice. Requirements vary by state, county and city — check with your accountant and local authorities. This checklist is a starting point, not an exhaustive list.