## Phase 1 - Business Setup
COFFEE CART STARTUP CHECKLIST — MOBILE ESPRESSO BAR & COFFEE CATERING
PHASE 1: BUSINESS SETUP & REGISTRATIONS
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Hire an accountant or bookkeeper and set up quarterly estimated taxes | Owner | Week 1 | Ask for catering experience. Estimated taxes are due quarterly; move a share of every event deposit into a tax savings account so the bill never surprises you.
☐ | Choose your legal structure: an LLC, with or without an S corp election | Owner / Accountant | Week 1 | An LLC separates personal and business liability, which matters when you serve hot drinks and run a generator at other people's events. An S corp election can cut self-employment tax once profit is steady; ask your accountant when it pays off.
☐ | File your LLC with the Secretary of State and appoint a registered agent | Owner / Attorney | Weeks 1-2 | File the articles of organization online and sign an operating agreement, even for a single-member LLC. Fees and processing times vary by state; check your Secretary of State website.
☐ | Get your EIN from the IRS and register for state payroll and unemployment tax | Owner | Weeks 2-3 | Apply once the state approves your LLC. The EIN is free and takes minutes at irs.gov. Register with your state workforce agency before your first hire, so your payroll provider can file from day one.
☐ | Open a business bank account and keep finances separate | Owner | Weeks 2-3 | Bring your EIN letter and formation documents. Keep a card for purchases and a separate account for event deposits, so client money never mixes with personal money.
☐ | Get a seller's permit and register for state sales tax | Owner / Accountant | Weeks 2-4 | Apply on your state tax agency website. Hosted bookings are usually taxed as catering, and in many states that means the whole invoice: coffee, baristas, extras and travel. At festivals and farmers markets you collect tax drink by drink, and you may need to register where you sell. Check your state's rule before you quote.
☐ | Apply for the city or county business license (and a DBA if you use a trade name) | Owner | Weeks 2-4 | Check every city where you plan to cater: some require their own license to operate there. A DBA (fictitious business name) is filed with the county clerk or the state, depending on where you are.
☐ | Take this plan to two lenders and apply for your loan (bank or SBA 7(a)) | Owner / Accountant | Weeks 3-6 | Bring the Word plan, the Excel projections and written quotes for the cart, the espresso machines, the grinders and the trailer. SBA 7(a) loans go through participating banks: ask what owner equity they expect and how long approval takes, and do not buy the cart before the plan review and the loan are approved.
☐ | Have an attorney review your coffee catering service agreement, starting from the kit's template | Owner / Attorney | Weeks 3-6 | Start from the contract in this kit. Ask for a retainer of 30-50% to hold the date and credit it toward the price, the balance due 14 days before and the final guest count 10 days before. Add cancellation tiers with no gaps, service hours and the price of an extra hour, the outlet (110V or 220V, within a set number of feet) or a generator fee, a travel fee beyond your free radius, alt milks, a rain plan and the certificate of insurance for the venue. Reuse it for every event.
☐ | Write your HACCP-based food safety plan for the cart, with a written cold holding procedure for milk | Owner / Lead barista | Weeks 4-6 | Milk is a TCS food: keep it at 41 °F (5 °C) or below (FDA Food Code minimum) in the refrigerator and in the coolers, and date every opened container. Use potable water from an approved source in food-grade tanks, wash your hands first, and wipe and purge the steam wand and clean the pitchers between drinks. Flag the allergens: milk, soy and tree nuts, plus wheat and egg in pastries. Buy pastries only from a licensed bakery.
☐ | Get your Certified Food Protection Manager certificate (ServSafe Manager) | Owner / Lead barista | Weeks 4-6 | Most health departments require one certified manager. Take an ANSI-accredited exam and keep a copy for your permit file and for every event binder.
| Tasks completed: | 0 | of | 11

## Phase 2 - Permits & Commissary
COFFEE CART STARTUP CHECKLIST — MOBILE ESPRESSO BAR & COFFEE CATERING
PHASE 2: COMMISSARY, CART & TRAILER, HEALTH PERMIT & INSURANCE
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Choose a permitted commissary: water fill and gray water dump, milk refrigeration, dry storage and a place for the cart and the trailer | Owner | Weeks 1-3 | Visit at least three and ask first: can you fill potable water and dump gray water here, is there cold storage for milk, and where do the cart and the trailer stay? Compare hours, storage and the deposit. Do you need a commissary for a coffee cart? Usually yes, though some counties exempt self-contained units, so ask yours in writing (California's rule is Health & Safety Code §114295; Washington has an exemption under RCW 43.20.148, as examples). Never prep or store from home.
☐ | Sign a written commissary agreement | Owner | Weeks 2-4 | Your health department asks for it with the permit application. It should name your hours, water fill and gray water dump, storage for the cart and the trailer, and cleaning duties. Keep a signed copy on file, and a commissary log on board where your county asks for one (Washington does).
☐ | Apply for the mobile food unit permit and get the plan review BEFORE you buy the cart | Owner | Weeks 3-8 | Ask the county for its plan review checklist: NSF certifications, tank sizes, handwashing sink, refrigerator and an electrical plan. As an example, Snohomish County, WA charges $1,100 for the plan review and $500-1,025 for the annual permit, and wants electrical approval first. Ask whether a cart at private catered events counts as a mobile food unit or as a caterer in your county.
☐ | Get temporary food event permits for community or public events | Owner | As needed, 2-4 weeks ahead | Your mobile food unit permit does not always cover a festival. Each public or community event may need its own temporary food permit; ask the county health department and the organizer how far ahead to apply.
☐ | Check with your fire marshal about the generator and any propane | Owner / Lead barista | Weeks 4-8 | Without grease vapors you do not need a hood, but a generator does have rules. As an example, NFPA 96 guidance (summary) keeps a generator at least 12 ft (3.7 m) from the unit and 10 ft (3 m) from buildings, with an extinguisher on hand, and New Jersey asks for a permit each time you set up with a generator. Rules differ by city and fire district: ask your fire marshal.
☐ | Buy your espresso cart with the plan review checklist in hand | Owner | Weeks 3-8 | Make sure it matches what your county approves: NSF certification, a handwashing sink, potable and gray water tanks of the size your county asks for, and an under-counter refrigerator. If you buy a used cart, have an equipment technician inspect it and check for liens.
☐ | Title and register the trailer, and buy commercial auto and equipment-in-transit coverage | Owner / Insurance broker | Weeks 4-8 | Register the trailer at your state DMV in the business name. Commercial auto must cover the tow and the trailer; inland marine covers the cart, the machines and the grinders in transit. Check your vehicle's towing capacity and the hitch rating.
☐ | Buy and fit out the enclosed trailer: ramp, E-track anchors, wheel chocks for the cart, shelving and wrap | Owner | Weeks 6-10 | Fit E-track anchors and wheel chocks so the cart and the portable bar travel strapped down, add shelving and non-slip liners so loads cannot shift, and put on your logo wrap. Check that your insurer covers the fit-out.
☐ | Buy general liability (or a business owner's policy) and order certificates of insurance | Owner / Insurance broker | Weeks 4-8 | Ask in writing for a general liability or BOP policy of $1M per occurrence and $2M aggregate with unlimited additional insureds. Venues and planners ask for a certificate of insurance (COI) naming them as additional insured; ask your broker for same-day COIs.
☐ | Set your alcohol policy: no espresso martinis or liquor in your drinks without a license | Owner / Insurance broker | Weeks 4-8 | You cannot sell alcohol without a liquor license, so refer espresso martini requests to a licensed mobile bar (see the Mobile Bar Business Plan Kit). Ask your broker how your general liability policy treats alcohol you do not sell, so there are no surprises if a host brings their own.
☐ | Buy workers' compensation coverage before your first hire | Owner / Insurance broker | Weeks 3-5 | Required in almost every state once you have employees, including part-time event baristas (Texas is the exception: optional there, but venues and lenders often ask for it). Premiums depend on payroll and class code.
☐ | Set up your waste plan: gray water, coffee grounds and milk containers | Owner | Weeks 6-10 | Dump gray water only at the commissary, never in a venue's sink or a storm drain. Send coffee grounds to compost where your commissary or city offers it, and recycle milk containers. Ask the commissary what it already handles.
☐ | Arrange pest control with a licensed company and post required notices | Owner | Weeks 6-10 | Usually through the commissary. Keep service records and post the permit and any required notices where inspectors expect them.
| Tasks completed: | 0 | of | 13

## Phase 3 - Equipment
COFFEE CART STARTUP CHECKLIST — MOBILE ESPRESSO BAR & COFFEE CATERING
PHASE 3: EQUIPMENT & SETUP
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | List what you own versus what you rent for each service style | Owner / Lead barista | Weeks 1-2 | A full-service espresso bar, a self-serve coffee station with drop-off cold brew and a guest-pay pop-up need different equipment. Rent what you use rarely and buy what you use at nearly every event.
☐ | Buy under-counter refrigerators, coolers with ice packs, calibrated thermometers and airpots | Lead barista | Weeks 2-4 | Keep milk at 41 °F (5 °C) or below (FDA Food Code minimum) with an under-counter refrigerator at each station and coolers with ice packs for the reserve. Calibrate thermometers in ice water and keep spares in the trailer. Airpots keep batch brew hot through the service window.
☐ | Open wholesale accounts with a specialty roaster, a milk distributor and a compostable cup supplier | Lead barista | Weeks 2-4 | Buy coffee by the lb from a specialty roaster (roasted 1-3 weeks before the event) and milk and oat milk from a distributor or a cash-and-carry. Compare delivery minimums and price lists, and order compostable cups where your city requires them.
☐ | Buy the espresso machines (a 2-group at 220V plus a compact 2-group) and the grinders, then install and dial them in | Owner / Lead barista | Weeks 3-5 | Confirm the amps and the plug before your first event: the 220V machine needs a dedicated NEMA 6-20 circuit (15-17 A) and the compact one pulls about 14 A. Install both, dial in the grinders at 18 g (0.63 oz) in and 36 g (1.27 oz) out, and pull test shots. A room without a 220V circuit needs a generator.
☐ | Stock smallwares: milk pitchers, scales, tampers, knock boxes, shot glasses, towels and sanitizer | Lead barista | Weeks 3-5 | Buy pitchers in several sizes so you can steam 8 oz (240 ml) or 12 oz (355 ml) drinks without waste, plus scales, tampers, knock boxes, shot glasses, towels, sanitizer buckets and test strips. Standardize sizes so everything stacks and fits the trailer.
☐ | Set up your syrups, sauces, alt milks and tea: recipes, labels and an allergen list per drink | Lead barista | Weeks 3-5 | Write a recipe and a label for each house-made syrup, and decide which milks you carry (oat, almond, soy) and whether you serve chai. Keep an allergen list per drink: milk, soy and tree nuts, and oat is gluten-free only if certified. Plan milk in oz per drink (8 oz, or 240 ml) and in gallons per event.
☐ | Build the second station: portable espresso bar, menu and signage, cup display and condiment station | Lead barista | Weeks 4-6 | The second station takes the overflow at big events and covers indoor rooms. Set up the portable bar with a short menu and signage, a cup display and a condiment station. Bring cords and a power strip with GFCI, and the generator for outdoor events.
☐ | Plan your espresso water: food-grade tanks, pump and a filter or softener | Owner | Weeks 4-6 | Water quality decides how your drinks taste and how long your machines last. Use food-grade tanks and a pump, and add a filter or a softener depending on how hard your water is. Ask your county for the minimum tank volume, and plan the fill and dump routine at the commissary.
☐ | Choose compostable cups, lids, sleeves and napkins for your drinks | Owner / Lead barista | Weeks 4-6 | Buy compostable cups in 8, 12 and 16 oz (240, 355 and 475 ml) with lids, sleeves, wooden stirrers, napkins and cold cups. Use compostable items where your city requires them (Seattle, as an example), and skip foam. Test that the lids seal before you buy a case.
☐ | Log milk temperature at every station | Lead barista | Weeks 5-6 | Check the refrigerator thermometer at each station and write down the temperature when you load, when you set up and mid-service. Milk must stay at 41 °F (5 °C) or below (FDA Food Code minimum). Keep the logs after every event.
☐ | Set up your commissary space: shelving, labeling and FIFO | Lead barista | Weeks 5-7 | Label and date everything, and store first in, first out. Shared kitchens are inspected often, so a tidy, labeled space protects your permit.
☐ | Run a full test event with both stations at full speed | Owner / Lead barista | Weeks 7-9 | Simulate a line of guests with both stations running. Count drinks per hour per barista and how much coffee, milk and how many cups you use, then use those numbers to calibrate the kit calculator.
| Tasks completed: | 0 | of | 12

## Phase 4 - Staff
COFFEE CART STARTUP CHECKLIST — MOBILE ESPRESSO BAR & COFFEE CATERING
PHASE 4: STAFF & TRAINING
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Set a barista plan per event | Owner / Lead barista | Weeks 1-2 | One barista makes about 50-65 drinks an hour, so 2 baristas on 2 machines handle about 100, and 2-3 baristas cover around 250 guests (Flashquotes). Write the ratio down and use it to price labor in every quote.
☐ | Build a pool of part-time hourly event staff on W-2 payroll, not 1099 | Owner | Weeks 2-6 | Event baristas are usually employees, not contractors (FLSA economic reality test; California AB5). Misclassification brings back wages and penalties, so pay them hourly on W-2 payroll, never 1099.
☐ | Prepare offer letters, I-9 and W-4 for each hire, and check state minimum wage | Owner | At hiring | Complete Form I-9 within three business days of the start date and collect a W-4. Check state and local minimum wage and any minimum shift rules.
☐ | File new-hire reports with your state | Owner / Payroll provider | Within 20 days of hire | Every state requires one, usually within 20 days. Most payroll providers file it for you automatically; confirm that yours does.
☐ | Set up a payroll provider and workers' comp on payroll | Owner / Accountant | Weeks 3-5 | Connect payroll to your workers' comp policy so premiums follow actual hours. Set a clear pay schedule, including how event-night overtime is paid.
☐ | Set your service charge and gratuity policy | Owner / Accountant | Weeks 3-5 | A mandatory service charge is not a tip: the part paid out to staff is wages (IRS Rev. Rul. 2012-18). A gratuity is voluntary and goes to staff. Keep them on separate invoice lines and check your state's sales tax rule. Use a tip jar only if the host accepts it, and the tips belong to the team.
☐ | Get food handler cards for your whole team | Event baristas | Before the first shift | Many states and counties require a food handler card for anyone handling food. Cards are cheap, online and valid for about 2-3 years.
☐ | Train baristas on safety: steam and hot water burns, refueling the generator, cords and GFCI power strips | Owner / Lead barista | Weeks 4-6 | Teach everyone to avoid steam and hot water burns, to refuel the generator only when it is cold and away from guests, to tape down cords and trip hazards, and to plug into GFCI power strips. Name who watches the equipment at all times during service.
☐ | Cover OSHA basics: burns, lifting the cart and machines, towing the trailer and wet floors | Owner / Lead barista | Weeks 4-6 | Train staff to lift the cart and the machines with two people and up the ramp, to hitch and tow the trailer safely, and to watch for wet floors. Keep an injury log and a first-aid kit in the trailer and at every event.
☐ | Train your service protocol: menu, standards, latte art, greeting, line handling and allergens | Lead barista | Weeks 5-7 | Run a pre-event briefing every time. Set your standards: a double shot at 18 g (0.63 oz) in and about 36 g (1.27 oz) out, 8 oz (240 ml) milk drinks, latte art, a greeting and how to move the line. Label milk, soy and tree nuts, and wheat and egg in pastries; oat milk is gluten-free only if certified.
| Tasks completed: | 0 | of | 10

## Phase 5 - Marketing
COFFEE CART STARTUP CHECKLIST — MOBILE ESPRESSO BAR & COFFEE CATERING
PHASE 5: MARKETING & LAUNCH
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Create your brand, logo, a short menu and photos of the cart at real events | Owner | Weeks 1-4 | Keep the menu short: espresso classics, signature and seasonal drinks, cold brew, chai and hot chocolate, with oat milk included. Photograph the cart at real events and the latte art; photos sell catering far better than menus.
☐ | Build a website with packages, per-guest starting prices and a quote request form | Owner | Weeks 3-6 | Show packages by service style and a starting price per guest. A short form that asks for date, venue and guest count gets you better leads.
☐ | Set up your Google Business Profile and collect reviews | Owner | Weeks 3-4 | Pick the catering category and add your service area and photos. Ask every client for a review; local search brings many leads.
☐ | Create profiles on The Knot, WeddingWire and Zola | Owner | Weeks 4-6 | These are the main directories for wedding clients. Upload photos, list packages and answer inquiries within a few hours.
☐ | Join GigSalad, Thumbtack and The Bash for private parties | Owner | Weeks 4-6 | These marketplaces charge a commission or a cost per lead. Build it into your prices from the start and track your cost per booking.
☐ | Define your tasting policy for prospects | Owner / Lead barista | Weeks 4-6 | Decide who gets a tasting, how many guests attend and whether the fee is credited toward the booking. Track the bookings each tasting produces.
☐ | Create a proposal template with the kit calculator and track leads in your CRM | Owner | Weeks 4-6 | Build your quote in the kit calculator: cost per drink, price per guest and per service hour, baristas and power. Log every inquiry in your CRM and follow up within 48 hours. Pick software that sends the quote, collects the e-signature and takes the retainer by card or ACH.
☐ | Prospect corporate clients: office managers, HR and event planners | Owner | Weeks 5-10 | Make a list of nearby offices, coworking spaces and event planners and offer a free hour of espresso at an open house. Corporate events are about 69.3% of coffee cart bookings on Flashquotes and they fill your weekdays, so follow up every contact.
☐ | Post latte art and the cart at events on Instagram and social media | Owner | Ongoing from Week 5 | Share photos and short videos with the client's permission. Use text messages for quick follow-ups, and keep every inquiry in your CRM.
☐ | Make agreements with venues and wedding planners (preferred vendor lists) | Owner | Weeks 6-12 | Ask each venue how to join its preferred list. Offer a tasting for the planner; their referrals turn into weekend bookings.
☐ | Start a referral and review program for after each event | Owner | Weeks 8-12 | Send a thank-you message with a review link a day after the event. Offer something small to clients who refer a friend or a company.
☐ | Host a launch tasting for planners, venues and companies, and book a local bridal show | Owner / Lead barista | Month 3 | Host an open house with a coffee bar for planners, venue managers and corporate event buyers. Ask your local wedding venues when the next bridal show is and reserve a booth early.
| Tasks completed: | 0 | of | 12

## Phase 6 - First 90 Days
COFFEE CART STARTUP CHECKLIST — MOBILE ESPRESSO BAR & COFFEE CATERING
PHASE 6: FIRST 90 DAYS
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Hold the final planning call with the client 3 weeks out: guests, package, allergies and timeline | Owner / Lead barista | 3 weeks out | Confirm the guest count, service hours, menu and milks, allergies, power and who your contact is on the day. Send the summary in writing, and remember the final guest count is due 10 days before.
☐ | Check the venue 2 weeks out: outlet, floor, access, trailer parking and rules | Lead barista | 2 weeks out | Confirm the outlet (110V or 220V), its amps and how far it is from your station, a level floor, indoor or outdoor, access and an elevator for the cart, and where the trailer will park. A 220V machine needs a dedicated circuit, so settle it in writing. Ask the venue for its rules in writing, and photograph the space.
☐ | Collect the final balance before the event and invoice extras within 48 hours | Owner | Per contract, then within 48 hours | Collect the balance on the date in your contract (often 3 to 14 days before the event). Invoice overages within 48 hours and follow corporate invoices on their 30-day terms.
☐ | Order coffee, milk and cups with a buffer, and prep cold brew and syrups the day before | Lead barista | 1 week out, then the day before | Order coffee (roasted 1-3 weeks earlier) and milks with a small buffer, plus cups. Brew the cold brew (12-24 hours) and make the syrups at the commissary the day before, labeled and chilled, and build one production list with who does what.
☐ | Load the trailer from the checklist: cart and bar strapped down, machines, grinders, cords, generator and milk in coolers | Lead barista / Driver | Day of event, before departure | Check the cart and the portable bar are strapped down, then the machines, grinders, cords and generator, the milk in coolers at 41 °F (5 °C) or below, the water tanks filled at the commissary and the cups against the list. Write down the milk temperature when you load and again when you arrive.
☐ | Arrive 1-1.5 hours early and set up: handwashing first, then warm up the machines and dial in the grinders | Lead barista | Day of event | Set up the handwashing station first, then the cart and the portable bar; setup takes about 1 hour. Warm up the machines, dial in the grinders and pull test shots, then serve during the booked service window. Count the drinks you serve: the number feeds your weekly review.
☐ | Break down: backflush and clean the machines, steam wands and grinders | Lead barista / Event baristas | Day of event or next morning | Backflush the machines, clean the steam wands and the grinders, and dump gray water only at the commissary. Throw away opened milk that spent time above 41 °F (5 °C). At festivals and farmers markets, reconcile your sales with the organizer before you leave.
☐ | Ask for a review and photos; follow up in your CRM | Owner | Within 48 hours | Thank the client, share a review link and ask permission to use photos. Note preferences for the next booking.
☐ | Review every week: drinks per guest, drinks per hour per barista, coffee and milk used, cost per drink and hours per event | Owner / Lead barista | Weekly | Compare drinks per guest, drinks per hour per barista, coffee and milk used, cost per drink and staff hours with what the calculator projected. Small gaps add up quickly across a season.
☐ | Do your 90-day review: price per guest, guest minimums and packages | Owner | Day 90 | Look at which events earned the most, which took too long and which packages sold. Adjust prices, minimums and offers.
| Tasks completed: | 0 | of | 10

## Instructions
INSTRUCTIONS FOR USE
This file is part of the Coffee Cart Business Plan Kit by AI Chef Pro.
The GREEN cells are the editable ones: change those and the rest of the workbook recalculates on its own.
OK column: choose ✓ (done), ☐ (pending) or N/A (not applicable). N/A items do not count toward the total.
Each tab's counter counts only the ✓; N/A items come out of the total.
To edit a cell that is not green: Review → Unprotect Sheet (there is no password).
More templates and kits in the catalog at aichef.pro/en/digital-products
Designed by John Guerrero — chef and restaurant consultant since 2010, in the kitchen since age 17 · johnguerrero.es
Version 2.2 · October 2026 · aichef.pro/en/digital-products/coffee-cart-business-plan · info@aichef.pro
Planning tool, not financial, tax or legal advice. Requirements vary by state, county and city — check with your accountant and local authorities. This checklist is a starting point, not an exhaustive list.