## Phase 1 - Business Setup
CATERING STARTUP CHECKLIST — FULL-SERVICE EVENT CATERER
PHASE 1: BUSINESS SETUP & REGISTRATIONS
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Choose your legal structure with your accountant: LLC or S corp | Owner / Accountant | Week 1 | An LLC separates personal and business liability and suits partners. An S corp election can cut self-employment tax once profit is steady; ask your accountant when it pays off.
☐ | Get your EIN from the IRS and register for state payroll and unemployment tax | Owner | Weeks 1-2 | The EIN is free and takes minutes online at irs.gov. Register with your state workforce agency before your first hire, so your payroll provider can file from day one.
☐ | File your LLC with the Secretary of State and appoint a registered agent | Owner / Attorney | Weeks 1-3 | File the articles of organization and sign an operating agreement, even for a single-member LLC. Filing fees and processing times vary by state; check the state website.
☐ | Open a business bank account and keep finances separate | Owner | Weeks 2-3 | Bring your EIN letter and formation documents. Keep a card for purchases and a separate account for deposits, so event deposits never mix with personal money.
☐ | Get a seller's permit and register for state sales tax | Owner / Accountant | Weeks 2-4 | In many states sales tax applies to the whole catering invoice: food, staff and rentals. Confirm your state's rule and whether service charges are taxed before you quote.
☐ | Apply for the city or county business license (and a DBA if you use a trade name) | Owner | Weeks 2-4 | Check every city where you plan to cater: some require a license to operate there. A DBA (fictitious business name) is filed with the county or state.
☐ | Hire an accountant or bookkeeper and set up quarterly estimated taxes | Owner | Weeks 3-4 | Ask for catering experience. Estimated taxes are due quarterly; put a share of every deposit into a tax savings account so the bill never surprises you.
☐ | Choose catering software for proposals, contracts, deposits and invoices | Owner | Weeks 3-5 | One tool should send the quote, collect the e-signature and take the deposit by card or ACH. Test it with a mock proposal before you pay for a full year.
☐ | Have an attorney draft your standard catering contract | Owner / Attorney | Weeks 3-6 | Cover deposit, cancellation and postponement terms, guest minimum, final guest count date, and service charge versus gratuity. Reuse it for every event.
☐ | Write your HACCP-based food safety plan and transport SOPs | Owner / Executive chef | Weeks 4-6 | Document temperatures, cooling, reheating and hot and cold holding during transport. Your health department may ask for it at permit review.
☐ | Get your Certified Food Protection Manager certificate (ServSafe Manager) | Owner / Executive chef | Weeks 4-6 | Most health departments require one certified manager. Take an ANSI-accredited exam and keep a copy for your permit file and for every event binder.
| Tasks completed: | 0 | of | 11

## Phase 2 - Kitchen, Van, Permits
CATERING STARTUP CHECKLIST — FULL-SERVICE EVENT CATERER
PHASE 2: KITCHEN, VAN & PERMITS
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Choose a shared commissary kitchen: hours, cold and dry storage, van parking | Owner | Weeks 1-3 | Visit at least three. Compare peak-hour availability, walk-in space, parking for the van and the deposit. Ask whether the health department has approved the kitchen for catering.
☐ | Sign a written commissary agreement | Owner | Weeks 2-4 | The health department requires it. It should name your hours, storage areas, parking and cleaning duties. Keep a copy for the permit application.
☐ | Apply for the county catering / health permit | Owner | Weeks 3-8 | Plan review applies mainly if you lease your own kitchen. Expect an application, a fee, a menu review and an inspection of the kitchen and the van.
☐ | Get temporary food event permits for community or public events | Owner | As needed, 2-4 weeks ahead | Your catering permit usually does not cover public or community events. Each event may need its own temporary food permit; apply well before the date.
☐ | Check fire marshal rules for open flame, chafing fuel and tents | Owner / Executive chef | Weeks 4-8 | Rules depend on the venue and the city. Ask venues about open flame, fuel canisters and cooking under tents, and keep fire extinguishers on the van.
☐ | Buy a used refrigerated cargo van and have it inspected | Owner | Weeks 3-8 | Get a mechanical inspection and test the refrigeration unit under load. Check mileage, service records and payload, and read the title for liens.
☐ | Register and title the van and buy commercial auto insurance | Owner | Weeks 4-8 | Register it in the business name. A CDL is needed only when the gross vehicle weight rating is 26,001 lb or more, which a standard cargo van is not.
☐ | Upfit the van: shelving, load restraints and branding | Owner | Weeks 6-10 | Add racks, tie-downs and non-slip liners so loads cannot shift. A wrap helps marketing, but check that your insurer covers the upfit.
☐ | Buy general liability and business owner's policy coverage, and order certificates of insurance | Owner / Insurance broker | Weeks 4-8 | Venues and planners ask for a certificate of insurance (COI) naming them as additional insured. Ask your broker for same-day COIs.
☐ | Add liquor liability if you serve alcohol the client buys | Owner / Insurance broker | Weeks 4-8 | Skip it if no alcohol is served at your events. If your bartenders pour client-supplied alcohol, you need liquor liability and certified bartenders.
☐ | Buy workers' compensation coverage before your first hire | Owner / Insurance broker | Weeks 6-10 | Required in almost every state once you have employees, including part-time event staff. Premiums depend on payroll and class code.
☐ | Arrange waste and grease removal with a licensed hauler | Owner | Weeks 6-10 | The commissary often handles it. Confirm who removes grease and trash for the van and what you must label, store and log.
☐ | Arrange pest control with a licensed company and post required notices | Owner | Weeks 6-10 | Usually through the commissary. Keep service records and post the permit and any required notices where inspectors expect them.
| Tasks completed: | 0 | of | 13

## Phase 3 - Equipment
CATERING STARTUP CHECKLIST — FULL-SERVICE EVENT CATERER
PHASE 3: EQUIPMENT & SETUP
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | List what you own versus what you rent for each service style | Owner / Executive chef | Weeks 1-2 | Drop-off, buffet, family-style, plated and stations need different equipment. Rent what you use rarely and buy what you use at nearly every event.
☐ | Buy chafing dishes, insulated carriers and calibrated thermometers | Executive chef | Weeks 2-4 | Choose insulated carriers that hold food hot or cold for the whole trip. Calibrate thermometers and keep spares in the van.
☐ | Buy portable cooking and power: induction, burners and a generator | Executive chef | Weeks 3-5 | Venues rarely have enough power for heavy cooking. Induction units are quiet and safer indoors; use a generator only where fire rules allow.
☐ | Stock hotel pans, sheet pans and utensils | Executive chef | Weeks 3-5 | Standardize on hotel pan sizes so everything stacks, travels and fits the carriers. Label pans and lids by station.
☐ | Buy serving and presentation pieces for chef-attended stations | Executive chef | Weeks 4-6 | Platters, risers, signage and a small tool kit per station. A consistent look is what makes your themed stations memorable in photos.
☐ | Open accounts with a broadline distributor (US Foods, Sysco, Restaurant Depot) | Executive chef | Weeks 2-4 | Compare delivery minimums, credit terms and price lists. Restaurant Depot works well for small orders; broadline accounts cut costs as volume grows.
☐ | Line up specialty suppliers for your themed stations | Executive chef | Weeks 3-5 | Think of tortillas, proteins for carving, fresh pasta, fish for poke. Get quotes and delivery days from at least two suppliers per item.
☐ | Sign an agreement with a party rental company for tables, linens and dinnerware | Owner | Weeks 4-6 | Negotiate a caterer rate and standard delivery and pickup times. Rentals are billed to the client, so build them into your proposal.
☐ | Choose disposables and packaging for drop-off orders | Owner / Executive chef | Weeks 4-6 | Use compostable items where your city requires them. Test that hot food stays hot and that lids do not leak in a moving van.
☐ | Set up temperature logging for transport with a data logger | Executive chef | Weeks 5-6 | Place a logger in each carrier and in the van's cargo area. Save the report after every event as proof that food stayed in the safe zone.
☐ | Set up your commissary space: shelving, labeling and FIFO | Executive chef | Weeks 5-7 | Label and date everything, and store first in, first out. Shared kitchens are inspected often, so a tidy, labeled space protects your permit.
☐ | Run a full dry run of an event with your team | Owner / Executive chef | Weeks 7-9 | Cook, pack, load, drive and set up for a mock event at a friend's venue. Time every step and fix what was slow before a client sees it.
| Tasks completed: | 0 | of | 12

## Phase 4 - Staff
CATERING STARTUP CHECKLIST — FULL-SERVICE EVENT CATERER
PHASE 4: STAFF & TRAINING
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Set a staffing plan per event by service style (servers per guest) | Owner / Executive chef | Weeks 1-2 | Buffets need fewer servers than plated dinners. Write a servers-per-guest ratio for each style and use it to price labor in every quote.
☐ | Build a pool of event staff on W-2 payroll, not 1099 | Owner | Weeks 2-6 | Event servers and bartenders are usually employees, not contractors (FLSA economic reality test; California AB5). Misclassification brings back wages and penalties.
☐ | Prepare offer letters, I-9 and W-4 for each hire, and check state minimum wage | Owner | At hiring | Complete Form I-9 within three business days of the start date and collect a W-4. Check state and local minimum wage and any minimum shift rules.
☐ | File new-hire reports with your state | Owner / Payroll provider | Within 20 days of hire | Every state requires one, usually within 20 days. Most payroll providers file it for you automatically; confirm that yours does.
☐ | Set up a payroll provider and workers' comp on payroll | Owner / Accountant | Weeks 3-5 | Connect payroll to your workers' comp policy so premiums follow actual hours. Set a clear pay schedule, including how event-night overtime is paid.
☐ | Get food handler cards for your whole team | Event staff | Before the first shift | Many states and counties require a food handler card for anyone handling food. Cards are cheap, online and valid for about 2-3 years.
☐ | Get alcohol server certification for your bartenders (TIPS, ServSafe Alcohol or TABC) | Bartenders | Weeks 4-6 | Required or strongly recommended where alcohol is served. Insurers often ask for it, and it is a selling point for planners and venues.
☐ | Cover OSHA basics: burns, lifting and driving safety | Owner / Executive chef | Weeks 4-6 | Train staff on hot pans, safe lifting and loading, and van driving. Keep an injury log and a first-aid kit in the van and at every event.
☐ | Train service and event protocol: uniform, briefing and the nine major allergens | Executive chef / Event captain | Weeks 5-7 | Run a pre-event briefing every time. Everyone should know the nine major allergens and how to hand an allergy question to the chef.
☐ | Set your service charge and gratuity policy | Owner / Accountant | Weeks 3-5 | A mandatory service charge is wages (IRS Rev. Rul. 2012-18); a gratuity is voluntary and goes to staff. Keep them on separate invoice lines and check your state's sales tax rule.
| Tasks completed: | 0 | of | 10

## Phase 5 - Marketing
CATERING STARTUP CHECKLIST — FULL-SERVICE EVENT CATERER
PHASE 5: MARKETING & LAUNCH
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Create your brand, logo, themed station menu and professional photos | Owner | Weeks 1-4 | Photograph the stations, the plating and the team in action. Photos sell catering far better than menus, so invest here.
☐ | Build a website with menus, per-guest starting prices and a quote request form | Owner | Weeks 3-6 | Show packages by service style and a starting price per guest. A short form that asks for date, venue and guest count gets you better leads.
☐ | Set up your Google Business Profile and collect reviews | Owner | Weeks 3-4 | Pick the catering category and add your service area and photos. Ask every client for a review; local search brings many leads.
☐ | Create profiles on The Knot and WeddingWire | Owner | Weeks 4-6 | Both are the main directories for wedding clients. Upload photos, list packages and answer inquiries within a few hours.
☐ | Join ezCater to reach corporate clients | Owner | Weeks 4-6 | ezCater is a corporate catering marketplace that charges a commission on each order. Include that commission in your prices from the start.
☐ | Prospect corporate clients: office managers, HR and event planners | Owner | Weeks 5-10 | Build a list of nearby offices and drop off sample lunches. Repeat weekday orders make your base, so follow up every contact.
☐ | Make agreements with venues and wedding planners (preferred vendor lists) | Owner | Weeks 6-12 | Ask each venue how to join its preferred list. Offer a tasting for the planner; their referrals turn into weekend bookings.
☐ | Define your tasting policy for prospects | Owner / Executive chef | Weeks 4-6 | Decide who gets a tasting, how many guests attend and whether the fee is credited toward the booking. Track the bookings each tasting produces.
☐ | Post event photos on Instagram and social media | Owner | Ongoing from Week 5 | Share event photos with the client's permission. Use text or SMS for quick client follow-ups; keep inquiries in your CRM.
☐ | Create a proposal template with the kit calculator and track leads in your CRM | Owner | Weeks 4-6 | Your calculator gives the price per guest; the template turns it into a polished quote. Log every inquiry and follow up within 48 hours.
☐ | Start a referral and review program for after each event | Owner | Weeks 8-12 | Send a thank-you message with a review link a day after the event. Offer something small to clients who refer a friend or a company.
☐ | Host a launch event or showcase for planners and companies | Owner / Executive chef | Month 3 | Invite planners, venue managers and office managers to a tasting of your stations. It is your best single day of sales.
| Tasks completed: | 0 | of | 12

## Phase 6 - First 90 Days
CATERING STARTUP CHECKLIST — FULL-SERVICE EVENT CATERER
PHASE 6: FIRST 90 DAYS
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Hold the client briefing at D-21: guests, diets and event timeline | Owner / Event captain | D-21 | Confirm the guest count, dietary needs, service style, arrival time and who your contact is on the day. Send the summary in writing.
☐ | Visit the venue at D-14: access, kitchen, outlets and water | Event captain | D-14 | Check loading access, parking, elevator, power, water and fire rules. Photograph the space and note where stations and chafers will go.
☐ | Order ingredients at D-7 and D-1 and write the production list | Executive chef | D-7 and D-1 | Order against the final guest count and add a small buffer. Build one production list with prep times and who does what.
☐ | Complete the loading and transport checklist with temperatures | Executive chef / Driver | Day of event, before departure | Check carriers, pans, equipment and rentals against the list. Record food temperatures when you load and again when you arrive.
☐ | Set up 60-90 minutes before service and run the event | Event captain | Day of event | Arrive early, set up the stations and check hot and cold temperatures before guests arrive. Brief staff, then keep a service timeline.
☐ | Pick up, clean and return rentals | Event captain / Event staff | Day of event or next morning | Count and inspect rentals before you leave. Return them clean by the agreed time to avoid late fees.
☐ | Invoice the balance and collect within 24-48 hours; track deposits | Owner | Within 48 hours after the event | Send the final invoice right away, including any overages. Match deposits received against your quote and chase unpaid balances early.
☐ | Ask for a review and photos; follow up in your CRM | Owner | 1-3 days after the event | Thank the client, share a review link and ask permission to use photos. Note preferences for the next booking.
☐ | Review food cost and labor per event against the calculator every week | Owner / Executive chef | Weekly | Compare actual food, staff hours and rentals with what the calculator projected. Small gaps add up quickly across a season.
☐ | Do your 90-day review: price per guest, guest minimums and packages | Owner | Day 90 | Look at which events earned the most, which took too long and which packages sold. Adjust prices, minimums and offers.
| Tasks completed: | 0 | of | 10

## Instructions
INSTRUCTIONS FOR USE
This file is part of the Catering Business Plan Kit by AI Chef Pro.
The GREEN cells are the editable ones: change those and the rest of the workbook recalculates on its own.
OK column: choose ✓ (done), ☐ (pending) or N/A (not applicable). N/A items do not count toward the total.
Each tab's counter counts only the ✓; N/A items come out of the total.
To edit a cell that is not green: Review → Unprotect Sheet (there is no password).
More templates and kits in the catalog at aichef.pro/en/digital-products
Designed by John Guerrero — chef and restaurant consultant since 2010, in the kitchen since age 17 · johnguerrero.es
Version 2.2 · October 2026 · aichef.pro/en/digital-products/catering-business-plan · info@aichef.pro
Planning tool, not financial, tax or legal advice. Requirements vary by state, county and city — check with your accountant and local authorities. This checklist is a starting point, not an exhaustive list.