## Phase 1 - Business Setup
TACO SHOP STARTUP CHECKLIST
PHASE 1: BUSINESS SETUP & TAXES (weeks 1-4)
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Zoning check before signing: restaurant use, hood, seats and patio | Owner / Code consultant | Before signing the lease | Ask the city planning (zoning) office whether the zoning allows a restaurant with a flat-top griddle, trompos and a fryer, whether the space can take a Type I hood with a duct up to the roof, what occupancy load it allows, and whether the city permits patio seating on that street. Then ask the fire marshal in writing what the hood and fire suppression requirements are. With no exhaust path to the roof, there are no trompos, griddle or comal.
☐ | Decide gas or charcoal trompo BEFORE signing the lease (charcoal = solid fuel: separate exhaust, NFPA 96) | Owner | Before signing the lease | A gas trompo (the plan's case) works with a standard Type I hood, installed by a licensed gas contractor. A charcoal trompo, like a charcoal carne asada grill, is a solid-fuel appliance under NFPA 96: it needs a separate exhaust, a spark arrestor and daily ash removal. Ask the fire marshal in writing whether your space can take it.
☐ | Decide whether to buy tortillas or make your own BEFORE signing the lease | Owner | Before signing the lease | The plan buys its tortillas. Making them in-house takes a masa harina mixer or nixtamal mill, a tortilla machine or press, kitchen space and a dedicated tortilla maker; on cost alone it only pays off above about 656 tortillas a day (the Taco Cost & Trompo Yield Calculator in the kit runs the math with your prices). If you make them yourself, the equipment has to fit in the space.
☐ | Choose your legal structure: LLC vs S corp | Accountant | Week 1 | The financial plan assumes an effective income tax rate of 25% (21% federal plus state), as for a C corporation. An LLC taxed as a pass-through pays through your personal return instead, and early losses carry forward as net operating losses. Compare an LLC vs S corp election with your CPA, using the plan's numbers.
☐ | Form the LLC with your state and get the EIN | Attorney / CPA | Weeks 1-2 | Filing fees, annual reports and franchise taxes vary by state. Check your Secretary of State's website before you file.
☐ | Business license + sales tax permit (state and city) | Accountant | Week 2 | Register with your state revenue department for a sales tax permit and with your city or county for a business license. Some states also ask for a separate food seller or retail license. Rules, fees and timing vary by state, so confirm them with your CPA before you open and collect sales tax from your first sale.
☐ | State payroll and unemployment registration (and workers' comp insurance) | Accountant | Week 2 | Premiums depend on your state, your payroll and your job classes. Get quotes from your insurance broker or the state fund.
☐ | Apply for the beer & wine license (state + local) | Owner | Week 1 | Start in week 1: ask your state alcohol beverage control (ABC) agency and your city what they need, and file as soon as you sign the lease: state and local approval can take months, and costs and timelines vary widely. Never open counting on it, and add liquor liability to your insurance.
☐ | Business bank account and business card | Owner | Week 2 | Keep them separate from personal accounts: card terminal settlements, delivery marketplace payouts and supplier payments all run through them.
☐ | Accountant / bookkeeper and a POS that reports sales tax | Owner | Weeks 2-4 | Payroll and onboarding for your team. Pick a POS that calculates and reports sales tax by jurisdiction before you buy it, and ask your CPA how often your state wants sales tax returns.
☐ | Take the plan to two SBA 7(a) lenders and compare loan offers | Owner | Weeks 2-4 | Bring the complete financial plan, with the month-by-month cash flow. Ask for quotes on equipment leasing for the walk-in cooler and the kitchen line, and ask each lender about the SBA Microloan (up to $50,000) as a complement. Lenders usually expect an owner equity injection (often around 10% for SBA start-ups; many want 20-30%).
☐ | General liability, liquor liability, property and workers' comp insurance | Insurance broker | Before construction | Get quotes for general liability, liquor liability (if you will serve beer and wine), property and workers' comp. Tell the broker you cook on gas with trompos, a griddle and a fryer, and ask about equipment breakdown and spoilage coverage for the walk-in cooler.
| Tasks completed: | 0 | of | 12

## Phase 2 - Hood, Gas & Permits
TACO SHOP STARTUP CHECKLIST
PHASE 2: SITE, HOOD, GAS, PERMITS & PATIO (weeks 3-14)
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Choose the space: about 1,200 sq ft (111 sq m), second-generation if you can, with a possible hood and duct route to the roof | Owner | Weeks 3-6 | Dining area of about 480 sq ft (45 sq m) for 30 seats at the counter and tables, an open kitchen of about 215 sq ft (20 sq m) with the trompos in view, restrooms (one ADA-accessible) and storage; the patio adds 12 seats from April to October. Look for a street with foot traffic in the evenings and on weekends, near a campus or an entertainment district.
☐ | Check the electrical service and the gas capacity | Electrician / Utility | Before signing | Refrigeration, hood fans and makeup air, HVAC and the dish machine run on electric; trompos, griddle, comal and burners run on gas (natural gas or propane). A new gas service takes time: ask the utility for the lead time and the cost.
☐ | Confirm the hood and duct route to the roof with your mechanical contractor | Architect / engineer | Before signing | A dedicated, continuous, sealed duct to the roof, through a shaft or up an exterior wall, with the landlord's written approval if it crosses shared areas or the building exterior.
☐ | Negotiate the lease: free-rent period during build-out and security deposit | Owner | Before signing | The plan counts two months of rent before opening and a two-month security deposit. Ask for free rent while the build-out and the hood and duct are under way.
☐ | Lease with restaurant use, hood rights and a beer & wine license contingency | Owner / Attorney | Week 6 | It should say "restaurant" (or "taqueria with a kitchen"), approve the hood and duct work up to the roof, and be contingent on getting your beer & wine license if you plan to serve it.
☐ | Commission architect and MEP drawings, including the hood and duct | Architect / Engineer | Weeks 6-8 | Kitchen layout, electrical load, occupancy, ventilation, ADA accessibility, the gas line and the duct to the roof. Ask your city or county for its mechanical and fire code requirements for commercial kitchens.
☐ | Zoning approval and certificate of occupancy | Owner / City planning office | Before construction | Restaurants go through your city's own process: zoning approval first, then a certificate of occupancy after the final inspections. Ask the planning office which permits apply to your address and in what order.
☐ | Building permit for the build-out and the hood | Owner / City planning office | Weeks 6-8, before construction starts | The build-out and the hood run through their own building permit and inspections: ask the building department which drawings and sign-offs they require.
☐ | Apply for the patio / sidewalk café permit | Owner / City | Together with the zoning approval | Sidewalk and patio seating needs its own city permit, always applied for separately. Ask about the fee, the hours and the insurance requirements; the plan includes an example fee.
☐ | Licensed gas contractor + permit and inspection | Licensed gas contractor | During construction | Gas permit and inspection, plus start-up and testing of the trompos, griddle, comal and burners by the licensed contractor. Keep the inspection sign-off in your permit file and ask the contractor about periodic gas appliance service.
☐ | Type I hood, UL 300 suppression and makeup air (charcoal: solid-fuel rules) | Installer / Engineer | Weeks 8-12 | The hood and duct need a mechanical permit: check your local code for the duct route and where the exhaust discharges. A gas trompo (the plan's case) uses a standard Type I system; charcoal or any other solid fuel adds NFPA 96 requirements (separate exhaust, spark arrestor, daily ash removal). Ask the fire marshal in writing.
☐ | Kitchen and dining area build-out: smooth, washable surfaces | Contractor | Weeks 8-12 | Smooth, nonabsorbent walls, slip-resistant floors, washable ceilings, a handwashing sink with hands-free controls, restrooms (one ADA-accessible), and sound insulation if you have neighbors.
☐ | Plumbing, grease interceptor and HVAC | Installer | Weeks 8-12 | Hot and cold water in the kitchen, drains with a grease interceptor (the griddle and the fryer send a lot of grease down the line) and HVAC for the dining area. Check your sewer authority's rules.
☐ | Fire marshal sign-off of the hood and suppression system, plus a Class K extinguisher | Installer | Weeks 10-12 | Type I hood over the trompos, griddle, comal and fryer, with grease filters, a UL 300 fire suppression system and makeup air. Ask the installer for the airflow figures and the filter cleaning schedule. The fire marshal inspects and signs off; keep a Class K extinguisher within reach of the fryer.
☐ | Final inspections and certificate of occupancy | Licensed electrician / Inspector | During and after construction | The final sign-offs (electrical, gas, mechanical, fire and building) and the certificate of occupancy. Keep them together with the gas paperwork: your health department and your insurer may ask for them.
| Tasks completed: | 0 | of | 15

## Phase 3 - Kitchen & Health
TACO SHOP STARTUP CHECKLIST
PHASE 3: KITCHEN, TROMPO & HEALTH (weeks 6-14)
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Buy the trompos, flat-top griddle, comal and fryer | Owner | Weeks 6-8 | Gas vertical broilers (trompos), three- or four-burner models sized for the cones you will run (the plan's case uses 30 lb (13.6 kg) cones), a flat-top griddle, a comal and a fryer. Compare data sheets and prices from at least two restaurant-supply dealers, and ask for the gas load, delivery time and installation.
☐ | Buy refrigeration: walk-in cooler, freezer and refrigerated salsa prep table | Owner | Weeks 8-10 | Space for the marinated meat and the stacked cones, a freezer, and a refrigerated prep table that holds the salsas and salsa bar toppings at 41 °F (5 °C) or below.
☐ | Submit your plans for health department plan review, apply for the health permit and book the pre-opening inspection | Owner / Health department | Before construction starts | Submit your plans for plan review (Food Code 8-201.11) before construction, then apply for the health permit and book the pre-opening inspection. Requirements, fees and timing are set by your county or state. If you plan to sell tortillas or masa to other businesses, ask about wholesale food rules too.
☐ | Marinated cones held at 41 °F (5 °C) or below, date-marked | Consultant / Owner | Before opening | Marinated al pastor meat is a TCS food: keep it in the walk-in cooler at 41 °F (5 °C) or below. Log the marinating time and the stacking time of each cone and date-mark it.
☐ | Get your county's vertical broiler rules in writing (cook temp, max time on the broiler, leftover cone) and write your trompo SOP | Head taquero | Before opening | Counties differ: some use 145 °F (63 °C) and others 155 °F (68 °C) for pork on a vertical broiler, and chicken is 165 °F (74 °C). Take no figure as the rule until your health department confirms it. Probe at the start and midway through service, slice only the outer layer that has reached temperature, and put the maximum time a cone may stay on the broiler in your SOP.
☐ | Cut tomatoes, fresh salsas and guacamole at 41 °F (5 °C) or below | Prep cook | Before opening | Cut tomatoes are a TCS food, so pico de gallo and fresh salsas stay at 41 °F (5 °C) or below. Guacamole: treat it as TCS and ask your regulator. Prep in small batches. Avocado browning is a quality issue, not a safety one: use lime juice and film pressed on the surface.
☐ | Carnitas and guisados: hot holding, cooling and reheating | Prep cook | Before opening | Hot holding at 135 °F (57 °C) or above. Cool what you store with a written procedure that follows the Food Code cooling steps, and reheat to 165 °F (74 °C) within 2 hours. Log the temperatures.
☐ | Salsa bar: cold holding or TPHC with a written procedure, labels and utensils | Counter lead | Before opening | Clean container at every refill (never top off), put-out and discard times logged, and a separate utensil for each salsa. If you use time as a public health control (Food Code 3-501.19: 4 or 6 hours), you need a written procedure. Salsa macha gets its own spoon because it contains peanuts and sesame.
☐ | Ceviche or aguachile: parasite destruction by freezing or a supplier letter | Owner | If it is on the menu | Freeze the fish at the times and temperatures in Food Code 3-402.11 (ask your health department), or buy fish that arrives already frozen with a written supplier guarantee. Keep the record on file.
☐ | Cheese, crema and packaged tortillas held at the temperature on the label | Owner | Before opening | Dairy such as queso fresco and crema is TCS: hold it at 41 °F (5 °C) or below. Anything else goes at the temperature the manufacturer's label sets.
☐ | Traceability and records: lots, temperatures and suppliers | Owner | From the first purchase | Lot and date of the meat, tortillas and cheeses, the marinating and stacking time of each cone, cold and hot holding temperatures, and the supplier of each ingredient.
☐ | Recipe cards for each taco and salsa, with their allergens | Head taquero | Before opening | Wheat (the flour tortilla on the gringa, beer), milk (cheeses, crema), peanuts and sesame (salsa macha, moles), tree nuts (moles) and others depending on the recipe. Corn tortillas are naturally gluten-free, but a shared comal and fryer mean you never promise it. Cost each recipe with the Taco Cost & Trompo Yield Calculator.
☐ | Allergens on delivery marketplaces and on your website | Owner | Before you sign up | Allergen information has to be available before the guest orders online or through a marketplace. Check the listing of each taco on every marketplace and on your own website, and keep them in sync with your allergen cards.
☐ | Temperature of orders leaving the shop | Owner | Before the first order | Packaging that holds temperature in transit (hot at 135 °F (57 °C) or above, cold at 41 °F (5 °C) or below), also on marketplace deliveries. Pack in clamshells, foil and salsa cups, and check local packaging rules. Build-your-own orders (tortillas and filling packed separately) arrive better.
| Tasks completed: | 0 | of | 14

## Phase 4 - Staff & Allergens
TACO SHOP STARTUP CHECKLIST
PHASE 4: STAFF, TRAINING, SAFETY & ALLERGENS (weeks 10-14)
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Set pay rates against the state and local minimum wage and post the labor law posters | Accountant | Week 10 | Set pay rates against the state and local minimum wage and post the required labor law posters. Enter the state or local minimum wage in the "0. Assumptions" tab: payroll is hourly W-2, with overtime under FLSA and your state's rules.
☐ | Offer letters for full-time and part-time staff | Accountant | Before opening | With schedule, pay rate and role. Collect a W-4 and an I-9 (with identity documents) from every hire, the I-9 within 3 business days of the start date. Classify people correctly: a 1099 contractor who works your schedule at your address is a misclassification risk.
☐ | Hire the second taquero before opening | Owner | Weeks 10-12 | Have them learn the marinade, the cone stacking and the slicing with you before opening: if only you can run the trompo, one sick day closes the shop.
☐ | Time clock and overtime records | Owner | From the first hire | Keep hours for every employee, part-time included (FLSA recordkeeping). A time clock in the POS makes it simple; agree with your CPA how to store the records.
☐ | Schedule for both services and Saturday night | Owner | Week 12 | Lunch and dinner, Tuesday to Sunday, closed Mondays; Saturday night needs about five people.
☐ | Own delivery drivers: W-2 employees only | Accountant | If you deliver yourself | Your own drivers are employees on payroll (W-2), and because they drive their own cars on your behalf you also need hired and non-owned auto insurance (check your state). Do not treat them as independent contractors. Drivers for DoorDash, Uber Eats and Grubhub work for the marketplace, not for you.
☐ | Food handler cards and a Certified Food Protection Manager (CFPM) | Owner | Before opening | Training is the employer's job (there is no single official document to pull): hygiene, trompo and salsa temperatures, allergens and cross-contact. Get a CFPM certificate for the person in charge and food handler cards as your state requires.
☐ | Trompo training: marinade, cone stacking and slicing | Owner | Before opening | Adobo, layers, pineapple, lighting the burners, thin slicing of the cooked outer layer and portion size per taco: this is an investment, not an expense.
☐ | OSHA basics: safety plan and training | Insurance carrier / Consultant | Before opening | Cover cuts from the trompo knife, burns from the griddle and the fryer, gas, heat and lifting. Write a short safety plan and train the team on it (OSHA basics).
☐ | Employee health policy and first aid | Insurance carrier / Consultant | At hire | Have every new hire sign an employee health agreement (report illness symptoms; Food Code 2-201) and stock a first aid kit.
☐ | Allergen information on the menu or by staff script, with a written record | Owner | Before opening | In writing on the menu or, if staff give it verbally, backed by a written record kept on site and a sign telling guests to ask. Keep one allergen matrix up to date for the whole menu.
☐ | Allergen signs at the salsa bar | Counter lead | Before opening | Each salsa with its allergens in plain view of the guest: salsa macha contains peanuts and sesame. Review the signs every time a recipe changes.
☐ | Never promise a gluten claim with a shared comal or fryer | Owner | Before printing the menu | Corn tortillas are naturally gluten-free, but a comal, fryer or tongs shared with the flour tortillas break any promise (FDA rule 21 CFR 101.91 allows the claim only under 20 ppm). Say it this way: "corn tortillas are naturally gluten-free; ask about our fryer and griddle". Disclose the allergen and the cross-contact risk instead of promising.
| Tasks completed: | 0 | of | 13

## Phase 5 - Menu, Brand, Delivery
TACO SHOP STARTUP CHECKLIST
PHASE 5: MENU, BRAND, DELIVERY & SUPPLIERS (weeks 8-16)
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Decide the type of taqueria and its menu | Owner | Week 8 | A neighborhood taco shop without a trompo, with a trompo and a salsa bar (this plan), with its own tortilleria, or a taqueria-cantina that needs a full liquor license: each takes different capital, space and margin. A sit-down Mexican restaurant with a full bar is a different business; this kit is for counter service with beer & wine only.
☐ | A menu of 8-10 tacos, with taco costing | Head taquero | Weeks 10-14 | Cost every taco, the order of 3 and the gringa, not only the al pastor: carnitas, suadero and barbacoa yield less and avocado prices swing. Use the Taco Cost & Trompo Yield Calculator in the kit.
☐ | Sales tax on the menu: one rate in the example; check your state's to-go rules | CPA / Owner | Before opening | The plan uses a single example sales tax rate on all sales. Some states tax to-go food, soft drinks and alcohol differently: ask your CPA and set up each rate in the POS and on every marketplace.
☐ | Utensils and napkins on request for to-go orders | Owner | Before opening | Hand out utensils and napkins only when guests ask for them, and keep the to-go containers in stock; check your city's packaging rules.
☐ | Local packaging ordinances: fees and bans | Owner | Before opening | Many cities and states ban foam and single-use plastic or charge a fee for bags and containers. Check your city's packaging ordinance before you order to-go containers, and ask your supplier for compliant options.
☐ | Mexican specialty distributor (dried chiles, masa harina) + a backup | Owner | Weeks 8-12 | Dried chiles, achiote, masa harina and imported products can take weeks to arrive: get lead times in writing, hold safety stock and sign a second distributor. This is the real bottleneck of the business.
☐ | Tortilla supplier: lot, receiving temperature and a second supplier | Owner | Weeks 10-14 | Corn tortillas (nixtamalized) with lot and date, received at the temperature on the label and logged. Ask two manufacturers for samples and a price per case. The plan uses 6 in (15 cm) tortillas at a reference price, 360 per case: enter your own.
☐ | Sign up with the delivery marketplaces (DoorDash, Uber Eats, Grubhub) | Owner | Before opening | Read the commission (tiers vary by plan and zone on DoorDash, Uber Eats and Grubhub), how often they pay out, who pays for promotions and what the tablet costs. Set a ceiling on the share of your sales you will let marketplaces take, and write it down.
☐ | Prices for the marketplace and for pickup at the shop | Owner | Before opening | Calculate the margin of the order of 3 and the gringa on the marketplace, with its commission and the packaging. Pickup at the shop pays no commission: push it.
☐ | Trademark search and registration (USPTO) | Owner | Weeks 2-8 | Run a trademark search first to make sure the name is not registered in your class (restaurant services), and check your state's business name registry.
☐ | Brand identity, photos and website with the menu and allergens | Designer | Weeks 8-14 | Real photos of the trompo and the tacos; a website with the menu, allergens, hours, pickup ordering and a privacy policy for each channel.
☐ | Google Business Profile, social media and Mexican holidays | Owner | Before opening | Lunch and dinner hours, photos of the trompo and a reply to every review. On the calendar: Cinco de Mayo, Mexican Independence Day (September 15-16) and Day of the Dead (November 1-2).
☐ | Background music: ASCAP, BMI and SESAC licenses | Owner | Before opening | These are separate music licenses from performing-rights organizations, different from any city permit. Get all of them if you play music, or use a streaming service licensed for business.
| Tasks completed: | 0 | of | 13

## Phase 6 - Opening & 90 Days
TACO SHOP STARTUP CHECKLIST
PHASE 6: OPENING & FIRST 90 DAYS
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Open in January, Month 1 of the plan | Owner | Month 1 | The plan starts in January and the ramp-up falls on the slowest months, January and February: that is why working capital matters. If you open in another month, rotate the seasonality row of the "12-Month Cash Flow" tab.
☐ | Pest control | Licensed pest control operator | Before opening | Contract with a licensed pest control operator: it is part of the prerequisites of your written food safety plan.
☐ | Cleaning plan for the kitchen, the trompo and the salsa bar | Owner | Before opening | Trompo and drip tray, griddle, comal, fryer, hood filters, refrigerated prep table and salsa containers, each with its log.
☐ | Trial services with the full menu | Head taquero | Week before opening | Run several trial services to tune the marinade, the portion size per taco and the ticket times before opening.
☐ | Check temperatures and records on day one | Owner | Day 1 | Walk-in cooler, salsa prep table, hot holding for the guisados, the trompo probe and the cleaning sheet; correct any deviation before you serve.
☐ | Health inspection: written food safety plan and records at hand | Owner | From day 1 | Allergen cards, traceability, temperature and cleaning logs, training certificates (CFPM and food handler cards) and pest control reports.
☐ | Hood cleaning schedule (NFPA 96) | Owner / Maintenance contractor | From month 1 | Hood and duct cleaning by a certified contractor at the frequency NFPA 96 sets for your type of cooking (solid fuel and high volume need it more often); grease filters as often as your cleaning plan says.
☐ | Fire suppression inspection every 6 months and gas appliance service | Licensed gas contractor | On a set calendar | The fire suppression system needs a licensed technician's inspection every 6 months; schedule service of the gas appliances with your licensed contractor too. Write the dates on the calendar.
☐ | Measure the trompo yield and recalculate | Head taquero | Weeks 1-12 | Weigh the raw cone and the leftover at closing every day, log both on your daily production sheet, and take the average to the Taco Cost & Trompo Yield Calculator: measure in the calculator, recalculate in the plan.
☐ | Schedule for Saturday night and the peak dates | Owner | April | May is the peak of the year (Cinco de Mayo and the patio), and Mexican Independence Day and Day of the Dead bring their own rushes: plan the schedule and the stock ahead of time.
☐ | Review the delivery marketplace statement each month | Owner | Monthly | Sales, commission, promotions and packaging: if the marketplace share of your sales passes the ceiling you set, or its margin no longer covers the commission, trim the menu there or raise prices. Own drivers only as W-2 employees and only when the volume pays for them.
☐ | Compare actual sales and costs with the plan each month | Owner | Monthly | Covers per day, average check, cost of goods and labor against the P&L in the Excel; review the taco costing whenever the price of meat, tortillas or avocado changes.
☐ | Track cash flow month by month and the minimum balance | Owner | Monthly | January and February are the slowest months and coincide with the launch: look at the balance of each month before a big payment.
| Tasks completed: | 0 | of | 13

## Instructions
INSTRUCTIONS FOR USE
This file is part of the Taco Shop Business Plan Kit by AI Chef Pro.
The GREEN cells are the editable ones: change those and the rest of the workbook recalculates on its own.
OK column: choose ✓ (done), ☐ (pending) or N/A (not applicable). N/A items do not count toward the total.
Each tab's counter counts only the ✓; N/A items come out of the total.
To edit a cell that is not green: Review → Unprotect Sheet (there is no password).
More templates and kits in the catalog at aichef.pro/en/digital-products
Designed by John Guerrero — chef and restaurant consultant since 2010, in the kitchen since age 17 · johnguerrero.es
Version 2.2 · October 2026 · aichef.pro/en/digital-products/taco-shop-business-plan · info@aichef.pro
Planning tool, not financial, tax or legal advice. Requirements vary by state, county and city — check with your accountant and local authorities. This checklist is a starting point, not an exhaustive list.