## Phase 1 - Business Setup
BAR OPENING CHECKLIST — NEIGHBORHOOD BAR WITH SMALL PLATES
PHASE 1: BUSINESS SETUP & LEGAL STEPS
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Choose a legal structure (LLC vs S corp with your accountant) | Accountant | Week 1 | Most owners start with a single-member LLC; your accountant can tell you when an S corp election pays off
☐ | File articles of organization with your Secretary of State | Attorney | 1-3 days | Most states let you file online; check the name is available first
☐ | Appoint a registered agent and sign an operating agreement | Attorney / Accountant | 1-2 weeks | The state must approve the LLC first; then request your EIN from the IRS (free)
☐ | Get your EIN (IRS) and register for state sales tax (seller's permit) | Accountant | 1 day | Your accountant / bookkeeper picks your NAICS code (722410 drinking places or 722511 full-service restaurant), depending on whether the bar or table service weighs more
☐ | Register for state payroll tax withholding and unemployment insurance | Accountant | 1 day | Registration steps and unemployment insurance rates vary by state: confirm them with your state workforce agency and your accountant before your first payroll
☐ | Open a business bank account | Owner | 1-3 days | Keep personal and business finances separate
☐ | Get your city or county business license | City / county | 1-3 days | Needed before most permits; many cities let you file and renew online
☐ | Health permit application with your county or city health department (plan review, then inspection) | Health department | Variable | Most health departments want a plan review of your layout and equipment BEFORE you build out; a bar with a kitchen gets a food establishment permit and an inspection before opening. UK: register your food business with the council at least 28 days before you start (free) and expect a Food Hygiene Rating (0-5) after inspection in England, Wales and Northern Ireland; Scotland uses FHIS (Pass / Improvement Required)
☐ | Trademark registration (optional) | USPTO | Several months | Protect your bar's name
☐ | Privacy notice and a record of how you collect and store customer data (loyalty program, email, SMS) | Owner | Before opening | If you text customers you need their TCPA consent first. Keep a short record of what data you collect, why and where it is stored; banks and payment processors may ask for it
☐ | Set up your POS to collect and report sales tax by location | Accountant | Before opening | Your POS must calculate, collect and report sales tax correctly for your location. Check it before you buy the POS + handhelds budgeted on "Startup Costs"
| Tasks completed: | 0 | of | 11

## Phase 2 - Location & Licenses
BAR OPENING CHECKLIST — NEIGHBORHOOD BAR WITH SMALL PLATES
PHASE 2: LOCATION & LICENSES
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Search for and select a location | Owner | 1-3 months | Area with nightlife, foot traffic and room for a patio
☐ | Negotiate the commercial lease | Owner / Attorney | 1-2 weeks | Ask for 2-3 months of rent abatement during the build-out and a liquor license contingency, so rent does not start, or you can exit, if the license is late or denied.
☐ | Zoning check before signing | City / county | Variable | Confirm bar / restaurant use and any distance rules for alcohol (for example from schools or churches) BEFORE you sign
☐ | Apply for your liquor license right after signing the lease | Owner + attorney | Start right after signing the lease: often 3-12 months | Never a one-day step: state alcohol agency plus local approval. In quota states you buy or transfer an existing license, so start the search early
☐ | Sidewalk café / patio permit | City / county | 1-3 months | Outdoor seats can add sales; the permit renews on the schedule your city sets
☐ | Entertainment permit if live music or DJ | City / county | Varies by city | Only if you plan live music or a DJ; ask your city
☐ | General liability + liquor liability (dram shop) insurance | Insurance agent | 1 day | Your state or insurer sets the minimum limits for liquor liability (dram shop): ask your broker for quotes
☐ | Property insurance or business owner's policy (BOP) | Insurance agent | 1 day | Covers fire, theft and water damage
☐ | Noise ordinance check (residential neighbors) | Architect / engineer | 1-2 weeks | Important if homes are nearby: your city may set quiet hours and sound limits
☐ | Required public notices posted (health permit, liquor license, labor law posters) | Owner | 1 day | Your health department sets what must be displayed (for example a consumer advisory and allergen notice, or ingredient and allergen labels), and the federal and state labor law posters go in a common area. If you serve alcohol, your state liquor license and its posted notices apply: check with your state alcohol agency
☐ | Contract with a licensed waste / grease hauler | Owner | 2 weeks | Inspectors check it. Separate cardboard and organic waste, and store used fryer grease for your hauler: it cannot go down the drain
☐ | Licensed pest control contract | Owner | 1 week | Part of your HACCP-based food safety plan; keep the service reports for inspections
☐ | Security camera signage and contract with the security company | Owner | With the build-out | Post notices where your state requires them; check the rules on audio recording and keep footage only as long as you need it
| Tasks completed: | 0 | of | 13

## Phase 3 - Build-Out & Equipment
BAR OPENING CHECKLIST — NEIGHBORHOOD BAR WITH SMALL PLATES
PHASE 3: BUILD-OUT & EQUIPMENT
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Architect + MEP drawings, building permits and health department plan review | Architect / engineer | 1-3 months | Floor plans, specifications, mechanical, electrical and plumbing systems, hood exhaust
☐ | Build-out: floors, walls, ceilings | Contractor | 4-8 weeks | Washable, non-porous surfaces in the kitchen
☐ | Electrical service sized for the kitchen line and bar coolers | Electrician | 1-2 weeks | A commercial kitchen plus HVAC means a heavy load; have your electrician confirm capacity before you sign
☐ | Type I hood + UL 300 suppression (NFPA 96) | Installer | 1-2 weeks | Critical with a griddle and fryer: they produce a lot of grease-laden smoke
☐ | Plumbing, drainage and grease interceptor | Plumber | 1 week | Grease interceptor (plumbing review): usually required when you cook; your city sets the rules
☐ | HVAC (A/C + heating) | Installer | 1 week | A busy bar generates heat and needs good airflow
☐ | Draft beer system installation (4-6 taps) | Beer distributor | 1 week | A draft installer, sometimes arranged through your distributor, installs the lines and glycol; budget it yourself. Compare distributors (national, regional, craft); tied-house rules limit what a brewer can give you free
☐ | Buy kitchen equipment | Owner | 2-3 weeks | Griddle, fryer, oven, salamander and bain-marie
☐ | Buy refrigeration | Owner | 1-2 weeks | Walk-in + underbar coolers + freezer
☐ | Build the bar + small-plates counter | Carpenter | 3-4 weeks | Bar top with a small-plates display, draft station and sink
☐ | Furniture: dining room + patio | Supplier | 2-3 weeks | High-tops and standard tables, bar stools, patio
☐ | Install POS + handhelds | Supplier | 1 week | POS at the bar + handhelds for the floor
☐ | Decor, lighting, chalkboards | Interior designer | 2-3 weeks | Tile, wood, daily small-plates chalkboards
| Tasks completed: | 0 | of | 13

## Phase 4 - Staff
BAR OPENING CHECKLIST — NEIGHBORHOOD BAR WITH SMALL PLATES
PHASE 4: STAFF & TRAINING
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Define the org chart and shifts | Owner | 1 week | Overlapping evening shifts; build the schedule around the after-work rush, the evening peak and last call
☐ | Post job openings | Owner | 1-2 weeks | Look for a cook with small-plates experience
☐ | Screening and interviews | Owner | 2 weeks | Practical test: prepare 3 small plates in 20 minutes
☐ | Employment paperwork: offer letters, I-9 and W-4 | Accountant | 1 day | The state minimum wage applies (local, where higher); check the tip-credit rules for bartenders and servers
☐ | New-hire reporting to your state | Accountant | Per state deadline | Check your state's deadline; set up payroll withholding before the first paycheck
☐ | Food safety training for the whole team (food handler cards; certified food protection manager for the person in charge) | Owner | 1 day | Food handler card rules vary by state and county, and the person in charge usually needs a Certified Food Protection Manager certificate (for example ServSafe). Keep copies on file and document the training in your HACCP-based food safety plan
☐ | OSHA basics: safety plan and training | Owner or outside consultant | 1-2 weeks | Cover the basics: training on hot equipment, slips and burns, a first-aid kit and workers' compensation insurance (required in almost every state)
☐ | Small-plates kitchen training | Kitchen lead | 1-2 weeks | Standardize recipes, plating and timing
☐ | Bar service + responsible beverage service training (TIPS / ServSafe Alcohol) | Owner | 1 week | Pouring and draft service, cocktails and wine by the glass, small-plates service at the bar; checking IDs and cutting off guests
☐ | Allergen + food safety training (Food Code) | Owner | 1 day | 9 major US allergens (UK: 14), temperature logs, traceability
☐ | Time and payroll records for all employees (FLSA) | Accountant | From the first hire | Required by the FLSA (DOL); keep payroll and time records for the period that federal and state rules require
☐ | Tell the team how their time records and personal data are handled | Accountant | From the first hire | There is no single federal rule, but some states protect employee data: if your time clock scans fingerprints or faces, Illinois (BIPA) and a few other states require written notice and consent first. Keep payroll records secure
| Tasks completed: | 0 | of | 12

## Phase 5 - Marketing
BAR OPENING CHECKLIST — NEIGHBORHOOD BAR WITH SMALL PLATES
PHASE 5: MARKETING & LAUNCH
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Design your visual identity | Designer | 2-3 weeks | Logo, colors, typography and visual style
☐ | Google Business Profile (CRITICAL) | Owner | 1 day | Category: Bar. Add photos, hours and menu
☐ | Social media profiles (Instagram + TikTok) | Owner | 1 day | Instagram for cocktail and plate photos, TikTok for bar and kitchen videos
☐ | Basic website | Developer / designer | 1-2 weeks | With menu, location, reservations, hours
☐ | Professional photo shoot | Photographer | 1 day | Cocktails, small plates, the bar, the vibe, the patio
☐ | Design the drink + small-plates menu | Designer | 1 week | Printed menu + daily small-plates chalkboard + digital QR
☐ | Exterior signage | Sign maker | 1 week | Sign + sidewalk chalkboard + window vinyl
☐ | Pre-opening social media campaign | Owner | 2-4 weeks | Show the bar and kitchen prep, a countdown and an opening giveaway
☐ | Distributor accounts (beer, wine, spirits) | Owner | 2 weeks | Three-tier system: you buy from licensed distributors. Compare prices and delivery terms before you sign; tied-house rules limit free taps and equipment
☐ | Register on Google, Yelp, OpenTable / Resy | Owner | 1 day | OpenTable / Resy matter if you take reservations for dinner or groups
☐ | Opening event | Owner | 1 day | Invite neighbors, local food and drink creators and neighborhood press
☐ | Loyalty program | Owner | 1 week | Punch card (10th small plate free) or a points app
☐ | ASCAP / BMI / SESAC music licenses if you play music in the bar | Owner | 2 weeks | Separate from the entertainment permit in this checklist: this is a copyright license, and you pay it even if your city has already approved your music or DJ
☐ | Privacy notice and consent on OpenTable / Resy and your email list | Owner | Before opening | Resy / OpenTable, SMS and newsletters collect personal data: each channel needs its own notice, and texting customers requires TCPA consent
| Tasks completed: | 0 | of | 14

## Phase 6 - First 90 Days
BAR OPENING CHECKLIST — NEIGHBORHOOD BAR WITH SMALL PLATES
PHASE 6: FIRST 90 DAYS
OK | TASK / ACTION | RESPONSIBLE | TIMING | NOTES
☐ | Review the daily register and sales | Owner | Daily | Compare against the forecasts in your business plan
☐ | Weekly food and pour cost check | Owner + kitchen lead | Weekly | Count bottles and kegs to track pour cost; weigh meat, fish and charcuterie
☐ | Analyze your best-selling vs. worst-selling small plates | Owner | Month 1 | Apply menu engineering: Stars, Plowhorses, Puzzles, Dogs
☐ | Adjust the daily small-plates menu | Kitchen lead | Weekly | Rotate small plates by season and available product
☐ | Guest surveys + Google and Yelp reviews | Owner | Month 1-3 | Ask for reviews and answer ALL of them
☐ | Optimize staff schedules | Owner | Month 1-2 | Reinforce Friday-Saturday, cut Monday-Tuesday
☐ | Review suppliers and negotiate | Owner | Month 2 | With real volume, renegotiate beer and wine prices with your distributors
☐ | Evaluate delivery (DoorDash, Uber Eats) for food only | Owner | Month 2-3 | Only if the margin allows: commissions are steep, and alcohol delivery depends on state law
☐ | Analyze local competition | Owner | Month 1 | Visit other bars nearby and compare
☐ | First quarter close and first sales tax return | Accountant | Month 3 | Compare actual P&L against the financial plan
| Tasks completed: | 0 | of | 10

## Instructions
INSTRUCTIONS FOR USE
This file is part of the Bar Business Plan Kit by AI Chef Pro.
The GREEN cells are the editable ones: change those and the rest of the workbook recalculates on its own.
OK column: choose ✓ (done), ☐ (pending) or N/A (not applicable). N/A items do not count toward the total.
Each tab's counter counts only the ✓; N/A items come out of the total.
To edit a cell that is not green: Review → Unprotect Sheet (there is no password).
More templates and kits in the catalog at aichef.pro/en/digital-products
Designed by John Guerrero — chef and restaurant consultant since 2010, in the kitchen since age 17 · johnguerrero.es
Version 2.2 · October 2026 · aichef.pro/en/digital-products/bar-business-plan · info@aichef.pro
Planning tool, not financial, tax or legal advice. Requirements vary by state, county and city — check with your accountant and local authorities. This checklist is a starting point, not an exhaustive list.