## Instructions
03 · Catering Event Manager Checklist + Quarterly & Annual Compliance
How to use this template:
▸ Complete checklist for the catering director or event manager.
▸ It covers everything from the first meeting with the client to the post-event wrap-up.
▸ It includes team coordination, the run sheet and quality control.
Customization:
▸ Adjust the timing to your usual type of event.
▸ Use the notes section for incidents.
Beyond the event:
▸ The "Quarterly & Annual" sheet covers what is CONTRACTED and what an inspector asks for in writing: commissary pest control, hood and exhaust ducts (NFPA 96), fire extinguishers and hood suppression, gas lines, vehicles (registration, insurance, county permit if required), thermometer calibration, used oil, health permits, food handler cards and Certified Food Protection Manager, insurance and invoicing / sales tax.
▸ Write the report number of each inspection and the date of the next one in "Notes"; the "Frequency" column already shows the legal or recommended interval for each.
▸ After the event, close out and validate the whole team's time-clock records, extras included: setup and breakdown are paid hours too. Keep time cards 2 years and payroll records 3 years (FLSA minimum; some states require longer, e.g. NY 6).
Designed by John Guerrero — chef and restaurant consultant since 2010, in professional kitchens since age 17 · johnguerrero.es
Version 2.0 · October 2026 · aichef.pro/en/digital-products/catering-checklist-templates · info@aichef.pro

## Event Manager
Director / Event Manager Tasks
AI Chef Pro · aichef.pro — Catering Checklists Kit Pro
Event Week (7 to 2 Days Out)
# | Task | Area | Assigned to | ✓ | Time | Notes
1 | Production meeting with the chef: confirm menu, quantities, run sheet | Office
2 | Confirm staff: number of servers, cooks, bartenders, runners (bartenders with the responsible-service training your state requires: TIPS, ServSafe Alcohol) | Office
3 | Send the team briefing: arrival time, dress code, contact | Office
4 | Confirm with the venue: load-in access, hours, facilities | Office
5 | Check equipment: smallwares, glassware, linens, decor | Office
6 | Prepare the floor plan for the room and setup with the table and station layout | Office
7 | Confirm outside vendors: florist, DJ, photographer, AV | Office
8 | Prepare the detailed event run sheet (minute by minute) | Office
Event Day — Before Service
# | Task | Area | Assigned to | ✓ | Time | Notes
1 | Arrive at the venue at least 3 h before the event starts | Office
2 | Check access (loading dock), power, potable water, restrooms, cold storage and the handwashing station | Office
3 | Coordinate the unloading and placement of the kitchen equipment | Office
4 | Supervise the room setup: tables, chairs, linens | Setup
5 | Check the buffet / station setup against the floor plan | Setup
6 | Pre-event briefing with the service team: timing, menu, allergens, VIPs | Office
7 | Pre-event briefing with the kitchen team: order of service, temperatures | Office
8 | Final check-in with the client: confirm last-minute changes | Office
9 | Check that music, lighting and room temperature are right | Office
During the Event
# | Task | Area | Assigned to | ✓ | Time | Notes
1 | Control service timing: appetizers, entrées, dessert, coffee | Office
2 | Supervise plating quality and plate temperature | Office
3 | Coordinate buffet and station refills | Service
4 | Handle incidents: unplanned allergens, last-minute changes | Office
5 | Stay in contact with the client and the wedding planner / organizer | Office
6 | Supervise bar and beverage service | Service
7 | Control plate clearing times between courses | Service
8 | Check guest satisfaction (discreet walk-around) | Office
After the Event
# | Task | Area | Assigned to | ✓ | Time | Notes
1 | Supervise an orderly breakdown and the venue cleanup | Breakdown
2 | Check the inventory of equipment picked up against what was delivered | Office
3 | Log incidents, breakage and waste | Office
4 | Confirm with the venue that the space is left in good condition | Office
5 | Send a thank-you to the client (24–48 h after the event) | Office
6 | Retrospective meeting with the team (feedback and improvements) | Office
7 | Close out and validate the time-clock records of the whole event team, extras included (setup, service and breakdown), and file them with the month's: keep time cards 2 years and payroll records 3 years (FLSA minimum; some states require longer, e.g. NY 6) | Office
8 | Update the event P&L: actual costs vs. budget | Office
| Tasks done: | 0 | of | 33
Signed off by: _________________ Date: ___/___/______
© 2026 AI Chef Pro · aichef.pro

## Quarterly & Annual
Quarterly & Annual Maintenance — Contracted Services
AI Chef Pro · aichef.pro — Catering Checklists Kit Pro
Hygiene & Pests — Licensed Contractor
# | Task | Area | Assigned to | ✓ | Frequency | Notes
1 | Pest control of the commissary by a licensed operator: service visit and signed service report on file | Office |  |  | Monthly
2 | Hood and duct cleaning by a certified contractor (NFPA 96: quarterly if high volume or charbroil, semiannual if moderate) | Office |  |  | Semiannual
3 | Optional lab testing of surfaces and product (environmental swabs or product analysis) to verify your cleaning plan; not required in the US | Production |  |  | Semiannual
4 | Review the HACCP plan (food safety plan) and the supplier files: additions, removals and menu changes over the year (templates in the HACCP Food Safety Kit Pro) | Office |  |  | Annual
5 | Renew food handler cards where your state or county requires them, keep at least one Certified Food Protection Manager (e.g. ServSafe Manager) on staff (FDA Food Code 2-102.12) and file the cards of regular extras | Office |  |  | Annual
6 | Check that the commissary's health permit (food service license) covers catering and is renewed per your county | Office |  |  | Annual
Vehicles & Cold Chain
# | Task | Area | Assigned to | ✓ | Frequency | Notes
1 | Vehicle registration and commercial auto insurance renewed; the health department's catering vehicle permit or inspection, if your county requires one | Transport |  |  | Annual
2 | Vehicle refrigeration unit serviced by a qualified tech: refrigerant, door seals and temperature recorder | Transport |  |  | Semiannual
3 | Calibrate thermometers and probes with the ice-point method (32 °F) and log the deviation | Production |  |  | Quarterly
4 | State vehicle inspection if your state requires it, and check the on-board fire extinguisher | Transport |  |  | Annual
5 | Deep clean and sanitize the vehicle with a signed record | Transport |  |  | Quarterly
Equipment, Gas & Waste
# | Task | Area | Assigned to | ✓ | Frequency | Notes
1 | Gas lines and appliance connections checked by a licensed pro if the kitchen has gas (as often as your local code requires) | Production |  |  | Annual
2 | Refrigeration service by an EPA 608-certified tech (walk-ins, reach-ins, blast chiller); ovens serviced per the manufacturer's schedule | Production |  |  | Annual
3 | Annual extinguisher maintenance by a licensed fire protection company: new tag and record (OSHA 1910.157); hood fire suppression inspected every 6 months (NFPA 96) | Office |  |  | Annual
4 | Used cooking oil pickup by a licensed recycler: file the pickup receipts | Production |  |  | Quarterly
Paperwork, Insurance & Invoicing
# | Task | Area | Assigned to | ✓ | Frequency | Notes
1 | Review your insurance: general liability (at the limits venues usually ask for), liquor liability if you serve alcohol, commercial auto and workers' comp; keep the COI (certificate of insurance) ready, with the venue as additional insured if it asks | Office |  |  | Annual
2 | This quarter's new hires: check each new event employee has Form I-9 (completed by their 3rd business day) and W-4 on file, and the time-clock records filed | Office |  |  | Quarterly
3 | Invoicing and POS software check: sales tax rates and settings, user permissions, updates | Office |  |  | Annual
4 | Update costing prices and event rates with real supplier prices | Office |  |  | Quarterly
5 | Write the report number of each inspection and the date of the next one in "Notes" | Office |  |  | Quarterly
| Tasks done: | 0 | of | 20
Signed off by: _________________ Date: ___/___/______
© 2026 AI Chef Pro · aichef.pro